- Dated: - CADENT GAS LIMITED - [CONTRACTOR]

- JCT 2024 Design and Build Contract (DB)

- in relation to a project at [ADDITIONAL DETAILS]

Key

Items to be completed prior to entering into the contract are highlighted yellow

- ARTICLES OF AGREEMENT

- THIS AGREEMENT is DATED

- BETWEEN:

- CADENT GAS LIMITED (a company registered in England) under registration number 10080864 whose registered office is at Cadent, Pilot Way, Ansty, Coventry CV7 9JU (‘the Employer’); and

- [CONTRACTOR] [(registered number [NUMBER]) whose registered office is at] [of] [ADDRESS] (‘the Contractor’).

- RECITALS

| - First: | the Employer wishes to have the design, construction, completion and defects rectification of [DESCRIPTION OF THE WORKS TO BE CARRIED OUT IN SUFFICIENT DETAIL] at [SITE ADDRESS] (‘the Works’) and the Employer has supplied to the Contractor documents showing and describing or otherwise stating its requirements (‘the Employer’s Requirements’). |
| --- | --- |
| - Second: | in response to the Employer’s Requirements the Contractor has supplied to the Employer documents showing and describing the Contractor’s proposals for the design and construction of the Works (‘the Contractor’s Proposals’); and an analysis of the Contract Sum (‘the Contract Sum Analysis’). |
| - Third: | the Contractor has examined the Employer’s Requirements and is satisfied that the Contractor’s Proposals meet the Employer’s Requirements. |
| - Fourth: | for the purposes of the Construction Industry Scheme (CIS) under the Finance Act 2004, the status of the Employer is, as at the Base Date, that stated in the Contract Particulars. |
| Fifth: | Not used. |
| Sixth: | where so stated in the Contract Particulars, this Contract is supplemented by the Framework Agreement identified in those particulars. |
| Seventh: | whether any of Supplemental Provisions 1 to 8 apply is stated in the Contract Particulars. |

- IT IS NOW AGREED THAT:

- Article 1: Contractor’s Obligations

- The Contractor shall complete the design for the Works and carry out and complete the construction of the Works in accordance with the Contract Documents.

- Article 2: Contract Sum

- The Employer shall pay the Contractor at the times and in the manner specified in the Conditions the VAT-exclusive sum of £[CONTRACT SUM IN FIGURES] ([CONTRACT SUM IN WORDS]) (‘the Contract Sum’) or such other sum as becomes payable under this Contract.

- Article 3: Collaborative Working

- The Parties shall work with each other and with other project team members in a co-operative and collaborative manner, in good faith and in a spirit of trust and respect. To that end, each shall support collaborative behaviour and address behaviour which is not collaborative.

- Article 4: Employer’s Agent

- For the purposes of this Contract, the Employer’s Agent is [NAME] of [ADDRESS] or such other person as the Employer nominates in its place. Save to the extent that the Employer may otherwise specify by notice to the Contractor, the Employer’s Agent shall have full authority to receive and issue applications, consents, instructions, notices, requests or statements and otherwise to act for the Employer under any of the Conditions.

- Article 5: Employer’s Requirements and Contractor’s Proposals

- The Employer’s Requirements, the Contractor’s Proposals and the Contract Sum Analysis are those referred to in the Contract Particulars.

- Article 6: CDM Regulations – Principal Designer and Principal Contractor

- For the purposes of the CDM Regulations:

the Principal Designer is the Contractor or such replacement as the Employer at any time appoints to fulfil that role; and

the Principal Contractor is the Contractor or such replacement as the Employer at any time appoints to fulfil that role.

- Article 7: Building Regulations – Principal Designer and Principal Contractor

- For the purposes of the Building Regulations:

the Principal Designer is the Contractor or such replacement as the Employer at any time appoints to fulfil that role; and

the Principal Contractor is the Contractor or such replacement as the Employer at any time appoints to fulfil that role.

- Article 8: Adjudication

- If any dispute or difference arises under this Contract, either Party may refer it to adjudication in accordance with clause 9.3.

- Article 9: Arbitration

- Arbitration does not apply.

- Article 10: Legal Proceedings

- Subject to Article 8 and (where it applies) to Article 9, the English courts shall have jurisdiction over any dispute or difference between the Parties which arises out of or in connection with this Contract (including any non-contractual obligations).

- Article 11: Incorporation of Conditions of JCT Design and Build Contract 2024

- This Contract includes the Conditions and Schedules comprised in the JCT Design and Build Contract 2024 (JCT DB 2024) (‘the Conditions’). The Conditions shall have effect as amended by the Schedule of Amendments at Appendix 1 to this Agreement (‘the Schedule of Amendments’).

- Article 12: Limitation

- Any action or proceedings for breach of this Contract which relates to a Building Safety Liability may be brought or commenced before the expiry of the limitation period which applies to the Building Safety Liability or the Civil Liability (Contribution) Act 1978; and the Parties shall not plead in defence of any such action or proceedings any shorter limitation period whether under the Limitation Act 1980 or otherwise. Any adjudicator’s decision under this Contract that has not already become final and binding, shall be final and binding on them unless either of the Parties has referred that dispute for final  determination by legal proceedings, or has commenced any action or proceedings to recover any overpayment to which the decision has led, within 12 years from the date of practical completion of the Works or the last date of practical completion of any Section.

- Article 13: Effect of approval

- Notwithstanding any other provision of this Contract, the Contractor shall not be relieved from its obligations under this Contract nor shall such obligations be removed, restricted, limited or qualified in any way by the presence of the Employer or the Employer’s Agent or its agents or representatives on the site of the Works, or the carrying out of tests on the instructions of the Employer or the Employer’s Agent or by any instruction, direction, admission, consent, approval, confirmation, sanction, acknowledgement, advice, payment, certificate or inspection made or given by or on behalf of the Employer or the Employer’s Agent.

- [Article 14: Novating Consultants

- Upon the execution of this Contract, the Employer, the Contractor and each of the Novating Consultants shall enter into a novation agreement executed as a deed in the form at Schedule 7, Part 1. The Contractor warrants to the Employer that, without limiting clause 3.3, it accepts entire responsibility for the work and designs of the Novating Consultants and for any negligence, omission or default on the part of the Novating Consultants whether prior or subsequent to the date of this Contract, as if such work, designs, negligence, omission or default were its own.]

- Article 15: Execution

- This Contract may be executed in any number of counterparts, each of which will constitute an original, but which together constitute one agreement.

- CONTRACT PARTICULARS

| - Clause etc. | Subject |  |
| --- | --- | --- |
| - Fourth Recital and clause 4.5 | - Construction Industry Scheme (CIS) | - Employer at the Base Date [is][is not] a “contractor” for the purposes of the CIS |
| - Sixth Recital | - Framework Agreement (if applicable) | - [DATE, TITLE, PARTIES] |
| - Seventh recital and Part 1 of Schedule 2 | - Supplemental Provisions - Part 1 |  |
|  | - Named Sub-Contractors | - Supplemental Provision 1 applies |
|  | - Valuation of Changes – Contractor’s estimates | - Supplemental Provision 2 applies |
|  | - Loss and expense – Contractor’s estimates | - Supplemental Provision 3 applies |
| - Seventh recital and Part 2 of Schedule 2 | - Supplemental Provisions - Part 2 |  |
|  | - Acceleration Quotation | - Supplemental Provision 4 applies |
|  | - Health and safety | - Supplemental Provision 5 applies |
|  | - Cost savings and value improvements | - Supplemental Provision 6 applies |
|  | - Performance Indicators and monitoring | - Supplemental Provision 7 does not apply |
|  | - Transparency | - Supplemental Provision 8 does not apply |
|  | - The Public Contracts Regulations 2015 | - Supplemental Provision 9 has been deleted |
| - Article 5 | - Employer’s Requirements - (State reference numbers and dates or other identifiers of the relevant documents.) | - [DESCRIBE] |
|  | - Contractor’s Proposals - (State reference numbers and dates or other identifiers of the relevant documents.) | - [DESCRIBE] |
|  | - Contract Sum Analysis - (State reference numbers and dates or other identifiers of the relevant documents.) | - [DESCRIBE] |
| - Article 9 | - Arbitration | - Article 9 and clauses 9.4 to 9.9 (Arbitration) do not apply |
| - 1.1 | - Base Date | - [DATE] |
|  | - BIM Protocol (where applicable) | - [TITLE, EDITION, DATE OR OTHER IDENTIFIERS] |
|  | - Date for Completion of the Works | - [DATE] |
|  | - Novating Consultants | - [Architect: - [NAME][(registered number [NUMBER]) whose registered office is] [of] [ADDRESS] - Structural Engineer: - [NAME][(registered number [NUMBER]) whose registered office is] [of] [ADDRESS] - [[Other Consultant]: - [NAME][(registered number [NUMBER]) whose registered office is] [of] [ADDRESS]] |
|  | - Sub-Contractors | - All sub-contractors with any responsibility for design, and such other sub-contractors as the Employer may from time to time by notice to the Contractor designate, together with the Contractor’s Design Team (including any Novating Consultants) |
| - 1.7.3 | - Addresses for service of notices etc. by the Parties | - Employer: Pilot Way, Ansty Park, Coventry, United Kingdom CV7 9JU - Contractor: [ADDRESS] |
|  | - The respective email addresses for the Parties are | - Employer’s email: [EMAIL ADDRESS] - Contractor’s email: [EMAIL ADDRESS] - or, subject to clause 1.7.3, such other email address as each Party may notify to the other from time to time |
| - 1.7.4.2 | - Service of notices by email | - Clause 1.7.4.2 does not apply |
| - 1.13 | The Contract Documents referred to in the Contract Documents List were shared via | [an email from [sender] to [recipient] on [date] at [time]] [a hyperlink [insert hyperlink(s) here] which was shared via an email from [sender] to [recipient] on [date] at [time]]] |
| - 2.3 | - Date of Possession of the site | - [DATE] |
| - 2.4 | - Deferment of possession of the site - (where possession by Sections does not apply) | - Clause 2.4 [applies][does not apply] - Maximum period of deferment (if less than 6 weeks) is [PERIOD] |
| - 2.17.3 | - Limit of Contractor’s liability for loss of use etc (if any) | - Contractor’s liability is not limited. |
| - 2.17B.1 | - Third Party Agreements | - Agreement 1: - [PARTIES, DATE, DESCRIPTION OF AGREEMENT] |
| - 2.29.2 | - Liquidated damages | - at the rate of £[FIGURES] per [day][calendar week or pro-rata for part of a week] |
| - 2.35 | - Rectification Period | - [12] months from the date of practical completion of the Works |
| - 2.37.1 | - As-built Drawings | - The number of complete sets of documents required is [NUMBER] |
| - 4.2, 4.12 and 4.13 | - Fluctuations Provision | - No Fluctuations Provision applies. |
| - 4.4.5 | - VAT | - The Employer’s VAT registration number is GB243133345 |
| - 4.6 | - Advance payment | - Clause 4.6 does not apply |
|  | - Advance Payment Bond | - An advance payment bond is not required |
| - 4.7 | - Method of payment - alternatives | - periodically in accordance with Alternative B (clause 4.13) |
| - 4.7.2 | - Interim Payments – Interim Valuation Dates | - The first Interim Valuation Date is: [DATE] - and afterwards the same date in each month or the nearest Business Day in that month |
| - 4.15.4 | - Listed Items - uniquely identified | - A bond is [required][not required] |
| - 4.15.5 | - Listed Items - not uniquely identified | - A bond is [required][not required] |
| - 4.17 | - Contractor’s Retention Bond | - Clause 4.17 does not apply |
| - 4.18.1 | - Retention Percentage | - [NUMBER] per cent |
| - 4.21.6 and 4.21.7 | - Relevant Matters | - Clause 4.21.6 (the effects of an epidemic on the execution of the works etc.) does not apply - Clause 4.21.7 (exercise of a statutory power etc.) does not apply |
| - 5.5 | - Daywork | - The Percentage Additions to each section of the prime cost, or if they apply in respect of labour, the All-Inclusive Rates, are set out in the following document - [DESCRIBE] |
| - 6.4.1 | - Contractor’s Public Liability insurance: injury to persons or property – the required level of cover is not less than | - £[FIGURES] for any one occurrence or series of occurrences arising out of one event |
| - 6.5.1 | - Insurance – liability of Employer | - Insurance [is][is not] required. - Minimum amount of indemnity for any one occurrence or series of occurrences arising out of one event - £[FIGURES] - [Other parties to be named as insured: [DESCRIBE]] |
| - 6.7 and Schedule 3 | - Works Insurance - Insurance Option applicable | - Schedule 3: - [Insurance Option A applies] - [Insurance Option B applies] - [Insurance Option C applies] |
|  | - Percentage to cover professional fees | [FIGURES] |
|  | - Where Insurance Option A applies and cover is to be provided under the Contractor’s annual policy (paragraph A.2) the annual renewal date is | - [DATE] |
|  | - Where Insurance Option C applies, paragraph C.1 | - applies |
| - 6.10 and Schedule 3 | - Terrorism Cover - details of the required cover | - are set out in the following document(s) [INSERT REFERENCE, DATE OR OTHER IDENTIFIER] |
| - 6.15 | - Professional Indemnity insurance |  |
|  | - Level of cover - (If an alternative is not selected the amount shall be the aggregate amount for any one period of insurance. A period of insurance for these purposes shall be one year unless otherwise stated.) | - Amount of indemnity required - [is for any one claim or series of claims arising out of one event] [is the aggregate amount for any one period of insurance] |
|  |  | - and is [FIGURES] |
|  | - Sub-limits within the overall level of cover | - [FIGURES AND DESCRIPTION] |
|  | - Specific exclusions listed in the relevant schedule(s) (or other policy document(s)) to the relevant policy | - [LIST EXCLUSIONS IF APPLICABLE] |
|  | - Expiry of required period of Professional Indemnity insurance is | - 12 years from the date of Practical Completion of the Works |
| - 6.17 | - Joint Fire Code | - The Joint Fire Code applies. |
|  | - If the Joint Fire Code applies, state whether the insurer under Insurance Option A, B or C (paragraph C.2) has specified that the Works are a “Large Project”: | - Yes. |
| - 6.20 | - Joint Fire Code - amendments/revisions | - The cost, if any, of compliance with amendment(s) or revision(s) to the Joint Fire Code shall be borne by the Contractor. |
| - 7.3.1 | - Performance bond or guarantee from bank or other approved surety | ## [is required][is not required] |
|  | ## The required form of the bond is set out in | ## Part 2 of Schedule 7 |
|  | ## Initial Value | ## [10] per cent of the Contract Sum |
|  | - Period of validity – if not specified in the required form, the expiry date of the performance bond or guarantee is to be | - [the date of practical completion of the Works] - OR - [2 weeks after the date of expiry of the Rectification Period for the Works] - OR - [the date of issue of the Notice of Completion of Making Good Defects for the Works] |
|  | - Reduction in value – if not specified in the required form and if expiring later than the date of practical completion of the Works, the percentage reduction in the initial value on that date is | - [50] per cent] |
| - 7.3.2 | ## Guarantee from the Contractor’s parent company | - [is required][is not required] |
|  | ## Parent company’s name and registration number | - [GUARANTOR] [(registered number [NUMBER]) whose registered office is at] [of] [ADDRESS] |
|  | ## The required form of the guarantee is set out in | - Part 3 of Schedule 7 |
| - 7.11 | ## Amount to be deducted for failure to provide collateral warranties | ## £[INSERT] for each collateral warranty |
| - 8.9.2 | - Period of suspension | - 6 months |
| - 8.11.1.1 to 8.11.1.7 | - Period of suspension | - 6 months |
| - 9.1 | - Notification and negotiation of disputes | - The respective nominees of the parties are: - Employer’s nominee [NAME] - Contractor’s nominee [NAME] - or such replacement as each Party may notify to the other from time to time. |
| - 9.3.1 | - Adjudication | - The Adjudicator is not named |
|  | - Nominating body - where no Adjudicator is named or where the named Adjudicator is unwilling or unable to act (whenever that is established) the nominating body is | - TECBAR |
| - 9.5.1 | - Arbitration - appointor of Arbitrator (and of any replacement) – the appointer is | - Does not apply |

APPENDIX 1: SCHEDULE OF AMENDMENTS

- Conditions

| - Section 1 | - Definitions and Interpretation |  |
| --- | --- | --- |
| - Clause 1.1 | - Delete the definition of “Agreement” and substitute: - “the Articles of Agreement consisting of the Recitals, the Articles, the Contract Particulars and Appendix 1 (Schedule of Amendments)”. |  |
|  | - In the definition of the “CDM Regulations” after “2015” and before the full stop insert: “and any related guidance requirements issued by the Health and Safety Executive from time to time”. |  |
|  | - Delete the definition of “Conditions” and substitute: - “the Conditions as defined in Article 11 to the Agreement.” |  |
|  | - In the definition of “Contractor’s Design Documents” in line 3 delete “the design of” and in line 5 delete “design”. |  |
|  | - In the definition of “Employer” before the full stop insert: - “its successors in title and permitted assignees.” |  |
|  | - Delete the definition of “Employer Rights”. |  |
|  | - Delete the definition of “Funder” and insert: - “any company, bank or institution providing finance in connection with or secured (whether by charge, sale and leaseback or otherwise) upon the Works, whether acting on its own account, as agent for a syndicate or other parties or otherwise.” |  |
|  | - Delete the definition of “Funder Rights”. |  |
|  | - In the definition of “Interest Rate” delete “5%” and insert: “3%”. |  |
|  | - Delete the definition of “PC Regulations”. |  |
|  | - Delete the definition of “P&T Rights”. |  |
|  | - Delete the definition of “Purchaser” and insert: - “any purchaser of the Works or each part of the Works”. |  |
|  | - Delete the definition of “Rights Particulars”. |  |
|  | - Delete the definition of “Statutory Provider” and insert: - “any local authority, utility service company or other statutory undertaker who has jurisdiction with regard to the Works or with whose systems the same are or will be connected and, where a Statutory Provider is carrying out work in relation to the Works not forming part of this Contract, includes any persons employed, engaged or authorised by it upon or in connection with that work.” |  |
|  | - Delete the definition of “Tenant” and insert: - “any tenant of the Works or each part of the Works.” |  |
|  | - Insert new definitions in alphabetical order: |  |
|  | - “Anti-Corruption Policy | - a policy implemented by the Contractor which sets out the procedures the Contractor has put in place to comply with section 7(2) of the Bribery Act 2010 and any guidance issued by the Secretary of State under section 9 of that Act.” |
|  | - “Anti-Slavery Policy | - a policy implemented by the Contractor which sets out the procedures the Contractor has put in place to comply with section 54 of the Modern Slavery Act 2015 and any guidance issued by the Secretary of State under section 54 of that Act.” |
|  | - “Associate | - “associated persons” and “associates” of the Employer, as such terms are defined by sections 121 and 131 of the BSA.” |
|  | - “Associated Persons | - any of the Contractor’s officers, employees, agents, sub-contractors, and any other persons who perform services for or on behalf of the Contractor in connection with this Contract.” |
|  | - “BSA | - the Building Safety Act 2022.” |
|  | - “Building Safety Liability | - any liability of the Contractor or the Employer that arises as a result of the BSA and/or the Defective Premises Act 1972 and/or section 38 of the Building Act 1984 whether under the Civil Liability (Contribution) Act 1978 or otherwise.” |
|  | - “Building Safety Regulator | - the Health and Safety Executive or such other body or individual as may be appointed from time to time to fulfil the role of building safety regulator for the purposes of the BSA, which term shall include any registered building inspectors and any other specialists appointed to assist the Building Safety Regulator in the carrying out of its regulatory duties in relation to the Works.” |
|  | - “Contractor’s Design Team | - any architect, civil and structural engineer, mechanical and electrical engineer, any Novating Consultant and any other professional consultant that the Contractor appoints to provide design services for the Works.” |
|  | - “Contract Documents List | - the list of Contract Documents set out in Schedule 8.” |
|  | - “Employer’s Anti-Slavery Policy | - the Employer’s anti-slavery policy available on the Employer’s website or upon request from the Employer.” |
|  | - “Intellectual Property | - all copyright and all neighbouring and database rights and moral rights, registered designs, registered and unregistered design rights, or any similar rights or property in any part of the world whether registered or unregistered together with the right to apply for the registration of such rights in any part of the world and the rights to current applications for registration of any such intellectual property.” |
|  | - “Nominating Notice | - a written notice in the form set out in Part 5C of Schedule 7 identifying the Third Party and the Third Party Rights vested in it.” |
|  | - “Novating Consultants | - those consultants identified as such in the Contract Particulars.” |
|  | - “Procurement Act 2023” | - the Procurement Act 2023 and implementing regulations.” |
|  | - “Programme | - the programme for the design, carrying out and completion of the Works in accordance with the Contract prepared to comply with any criteria specified in the Employer’s Requirements.” |
|  | - “Prohibited Materials | - any materials or substances other than in conformity with: - (a) the guidance given in the edition current at the date of specification and/or use of the publication “Good Practice in Selection of Construction Materials 2011” published by the British Council for Offices in March 2011; and - (b) relevant British Standards or Codes of Practice.” |
|  | - “Sub-Contractors | - those sub-contractors identified as such in the Contract Particulars.” |
|  | - “Third Parties | - Funders, Purchasers and Tenants and “Third Party” means any one of them.” |
|  | - [“Third Party Agreements | - the agreements listed in the Contract Particulars.”] |
|  | - “Third Party Rights | - the rights in favour of each Third Party set out in the Part 5A of Schedule 7.” |
| - Clause 1.3 | - After the full stop insert: - “This Contract constitutes the entire agreement between the Parties and supersedes all prior agreements, promises, assurances, warranties, representations and understandings between them, whether written or oral, relating to the Works, including but not limited to any letter of intent, letter of instruction or pre-construction services agreement (‘Prior Arrangement’). Any works or services performed by the Contractor prior to the date of this Contract under any such Prior Arrangement are deemed to have been performed under and subject to the terms of this Contract and not the Prior Arrangement and amounts paid under any such Prior Arrangement are to be treated as having been paid on account of the Contract Sum. - Each Party acknowledges that in entering into this Contract it does not reply upon, and shall have no remedy in respect of, any misrepresentation, representation, assurance, warranty or statement (whether made innocently or negligently) which is not expressly set out in this Contract. Each Party agrees that it shall have no claim for innocent or negligent misrepresentation or negligent misstatement based on any statement in this Contract, provided that nothing in clause 1.3 shall be interpreted as limiting or excluding the liability of any person for fraud or fraudulent misrepresentation.” |  |
| - Clause 1.3A | - Insert new clause 1.3A: |  |
| - “1.3A | - If there is any discrepancy or conflict between the Agreement, the Conditions, the Contract Documents and the Schedule of Amendments, the wording of the Schedule of Amendments will prevail. - If there is any discrepancy or conflict between the Contract Documents List and the content, revision and/or date of the documents transferred via clause 1.13, the Contract Documents List prevails.” |  |
| - Clause 1.4 | - Renumber clause 1.4.6 as clause 1.4.8, delete “and” at the end of clause 1.4.5 and insert new clauses 1.4.6 and 1.4.7: |  |
| - “1.4.6 | - any words following “include”, “includes”, “including”, “in particular” or any similar words or expressions shall be construed without limitation; |  |
| - 1.4.7 | references to the “reverse charge applying” (or similar) mean any case where the recipient of a supply for VAT purposes, or a member of a VAT group of which the recipient of the supply is a member, is required to account to the relevant tax authority for the VAT chargeable in respect of the supply; and” |  |
| - Clause 1.6 | - Delete and substitute: |  |
|  | “Except as provided in clause 7, and provided that any Associate may in its own right enforce a term of this Contract, nothing in this Contract confers or is intended to confer any right to enforce any of its terms on any person which is not a Party to it.” |  |
| - Clause 1.7.3.1 | Delete and insert: “Not used.” |  |
| - Clause 1.7.3.2 | After “.” and insert: “A copy of any notice sent shall also be delivered by hand or sent by pre-paid post to the recipient’s address stated in the Contract Particulars against clause 1.7.3, or to such other address as the recipient may from time to time notify to the sender, or if no such address is then current, the recipient’s last known principal business address or (where a body corporate) its registered principal office.” |  |
| - Clause 1.7.4.1 | Delete and insert: “Not used.” |  |
| - Clause 1.7.4.2 | After “.” and insert: “A copy of any notice sent shall also be delivered by hand or sent by Signed For 1st class or Special Delivery Guaranteed post (or any method of posting as had replaced either method and is then current).” |  |
| - Clause 1.8.1.1 | - Delete and insert: “Not used.” |  |
| - Clause 1.9 | - Delete “Save as stated in clause 1.8, no” and insert: “No”. |  |
| - Clause 1.10 | - Delete from “in the case of…” to the end of clause 1.10 and substitute: - “where this Contract expressly states that such consent or approval is at the discretion of the Party providing it.” |  |
| - Clause 1.11 | After “This Contract” insert: “and any non-contractual obligations arising out of or in connection with it”. |  |
| - Clauses 1.12 and 1.13 | Insert new clauses 1.12 and 1.13: |  |
| - “1.12 | Debts |  |
|  | “Any sum payable by the Contractor to the Employer as a debt under this Contract (including any interest payable on that debt) shall, for the purposes of any performance bond securing the Contractor’s performance under this Contract, constitute damages payable by the Contractor. |  |
| - 1.13 | Incorporation of Contract Documents |  |
|  | The Contract Documents listed in the Contract Documents List have been shared according to the method set out in the Contract Particulars. The Contractor acknowledges receipt of those Contract Documents and the Parties agree that they are incorporated by reference and form part of the Contract.” |  |

| - Section 2 | - Carrying out the Works |
| --- | --- |
| - Clause 2.1.1 | - In line 3 after “shall” insert: “carry out and”. - In lines 5 and 6 delete “so far as not described or stated in the Employer’s Requirements or the Contractor’s Proposals.” - At line 7 after “Statutory Requirements” insert: - “(and so not to put the Employer in breach of the Statutory Requirements)” |
| - Clause 2.1.3 | - After “shall pass to the Employer” insert: “within 7 days of their receipt”. |
| - Clause 2.1.5 | - After clause 2.1.5 insert new clauses 2.1.6 to 2.1.9: |
| - “2.1.6 | - Subject to clause 2.17.1.1, the Contractor shall ensure that the Works shall, when complete, comply with any performance specification or requirement included or referred to in the Contract Documents. |
| - 2.1.7 | - The Contractor shall take all reasonable steps to liaise with any Statutory Provider and shall be responsible for the co-ordination and integration of the design and execution of their works with the design and execution of the Works. |
| - 2.1.8 | - The Contractor shall take all reasonable steps to liaise with (and shall comply with the requirements of) the Building Safety Regulator. |
| - 2.1.9 | - In performing its obligations, the Contractor shall, and shall ensure that each of the Associated Persons shall, comply with the Modern Slavery Act 2015 and comply with the Anti-Slavery Policy. The Contractor shall take all reasonable steps to ensure that neither it nor any of the Contractor’s Persons shall place the Employer in breach of the Employer’s Anti-Slavery Policy.” |  |
|  | - After clause 2.2.6 insert a new clause 2.2.7: |
| - “2.2.7 | - The Contractor warrants to the Employer that in or in connection with the Works: |
|  | - 2.2.7.1 it has not used or permitted to be used or specified, and shall not use or specify for use or permit to be used any Prohibited Materials; - 2.2.7.2 it is not aware and has no reason to suspect or believe that Prohibited Materials have been or shall be used; and - 2.2.7.3 it shall promptly notify the Employer in writing if it becomes aware or has reason to suspect or believe that Prohibited Materials have been or shall be used. |
| - Clause 2.8 | - Renumber clause 2.8 as 2.8.1 and insert a new clause 2.8.2: |
| - 2.8.2 | 2.8.2.1 The Contractor shall provide the Employer with the Programme prior to the Date of Possession (or, if there are Sections, prior to the first of the Dates of Possession). The Contractor shall revise the Programme as appropriate from time to time, and if and whenever there is any material delay to the execution of the Works, so as to minimise or avoid any anticipated delay or disruption to the carrying out of the Works. The Contractor shall promptly provide the Employer with any revised Programme. 2.8.2.2 Each month the Contractor shall report to the Employer comparing the progress of the Works with the Programme current at that time, and promptly advise the Employer of any delay or disruption to the Works, setting out the measures it is taking or proposes to take to minimise or make good such delay or disruption.” |
| - Clause 2.11 | - Delete and substitute: |
|  | - “The Contractor shall be deemed to have verified all information contained in the Employer’s Requirements and to have obtained any supplementary information needed in respect of the Employer’s Requirements. The Contractor warrants that the Contractor’s Proposals meet the Employer’s Requirements.” |
| - Clause 2.12.1 | - Delete “and the Contractor under clause 2.11 is not responsible for verifying its adequacy”. |
| - Clause 2.12.2 | - Delete and insert: “Not used.” |
| - Clause 2.13 | - At the end of the clause insert: - “The Contractor shall comply with the Employer’s instructions without any increase to the Contract Sum (whether under clause 4.20 or otherwise) and without any extension to the Completion Date”. |
| - Clause 2.14.1 | - At the end of the clause insert: - “and without any extension to the Completion Date”. |
| - Clause 2.14.2 | - After “Contract Sum” insert: - “and without any extension to the Completion Date”. - Delete “and treated as a Change” and substitute: - “and the Contractor shall comply with the decision or acceptance by the Employer without any increase to the Contract Sum (whether under clause 4.20 or otherwise) and without any extension to the Completion Date”. |
| - [Clause 2.15.2.1 | - Insert at the end of the clause: - “provided that the Contractor shall not be entitled to any additional payment due to that Change (whether by way of an addition to the Contract Sum or otherwise) nor to any extension to the Completion Date if the relevant change in the Statutory Requirements ought to have been reasonably foreseeable to a contractor within the construction industry on or prior to the Base Date”. |
| - Clause 2.15.2.2 | - Delete from “such amendment” in the third line to the end of the clause and substitute: “such amendment shall be without cost to the Employer”.] |
| - [Clause 2.17.1.1 | - Delete clause 2.17.1.1 and substitute: - “The Contractor has exercised and shall continue to exercise in the design of the Works all reasonable skill and care as may be expected of a properly qualified designer of the appropriate discipline(s) for such design, experienced in carrying out works of a similar scope, nature, timescale and complexity. The Contractor accepts sole responsibility for the design of the Works and for the selection and standards of all materials, goods and workmanship forming part of the Works, including: (a) all and any design and other work undertaken in relation to the Works before the date of this Contract by any other person whether on behalf of the Contractor or by or on behalf of the Employer including that contained in the Employer’s Requirements; and (b) all and any design and other work undertaken in relation to the Works after the date of this Contract by any other person on behalf of the Contractor. - All such design and other work undertaken by any such person shall be treated for all the purposes of this Contract as undertaken by the Contractor. The Contractor also warrants that the Works, any Section and the site of the Works or any Section shall, as at the relevant date(s) of practical completion comply with all Statutory Requirements applicable at the Base Date.”] |
| - Clause 2.17A | - After clause 2.17 insert new clause[s] 2.17A [to 2.17B]: |
| - “2.17A | - Site Conditions |
| - 2.17A.1 | - The Contractor has had an opportunity of inspecting the physical conditions (including the sub-surface conditions and the presence and extent of any contamination, asbestos, cables, conduits, pipes or other services) and other conditions of or affecting the site of the Works (including the available means of access to and egress from the site) and shall fully acquaint itself with these conditions before the date of this Contract. The Contractor shall obtain all necessary information as to risks, contingencies and all other circumstances which may influence or affect the execution of the Works. Notwithstanding any other provision of this Contract, no failure on the part of the Contractor to discover or foresee any such condition, risk, contingency or circumstance shall entitle the Contractor to any additional payment (whether by way of an addition to the Contract Sum or otherwise) or to an extension of time. |
| - 2.17A.2 | - As between the Contractor and the Employer, the Contractor shall not and shall not be entitled to rely upon any survey, report or other document prepared by or on behalf of the Employer regarding any matter referred to in clause 2.17A. The Employer makes no representation or warranty as to the accuracy or completeness of and has no liability arising out of or in connection to any representation or statement made in such survey, report or document whether negligently or otherwise (but not fraudulently) made.[”] |
| - [2.17B | - Third Party Agreements |
| - 2.17B.1 | - Copies of relevant extracts of the Third Party Agreements (excluding matters related to price and payment) have been or shall be provided to the Contractor. |
| - 2.17B.2 | - The Contractor shall design, carry out and complete the construction of the Works in conformity with the Employer’s obligations under the Third Party Agreements including those relating to provision of information and the giving of notice and permitting inspections before the Practical Completion Statement or Section Completion Statement (as applicable) may be issued. |
| - 2.17B.3 | - The Contractor undertakes to the Employer that it has performed and shall continue to perform its obligations under this Contract in such manner and at such times so that no act, omission or default of the Contractor or any of the Contractor’s Persons (including the Novating Consultants if any) shall constitute, cause or contribute to any breach by the Employer of any of its obligations under the Third Party Agreements.”] |
| - Clause 2.20.2 | - Delete. |
| - Clause 2.25.1 | At clause 2.25.1 insert new sub-clause 2.25.1.3 as follows: |
|  | “2.25.1.3 and provided that any delay caused by a Relevant Event which is concurrent with another delay for which the Contractor is responsible shall not be taken into account,” |
| - Clause 2.25.6.5 | - Delete “.” after sub-clause 2.25.6.4 and insert “; and” and insert new sub-clauses 2.25.6.5 and 2.26.6.6: |
| - “2.25.6.5 | - the Contractor shall not be entitled to any extension of time for the completion of the Works or any Section to the extent that any circumstance arising by reason of any error, omission, negligence or default of the Contractor or any of the Contractor’s Persons has contributed to the delay; and |
| - 2.25.6.6 | - in assessing the extent of any extension of time any delay caused by a Relevant Event which is concurrent with another delay for which the Contractor is responsible shall not be taken into account.” |
| - Clause 2.26.2 | - Delete clause 2.26.2.1 and insert: “Not used.” - At the end of clause 2.26.2.2 insert: “(except to the extent that the Employer’s Requirements provide sufficient information to enable the Contractor to make a sufficient allowance prior to the issue of such instructions for the effects on programme of those instructions);” |
| - Clause 2.26.4 | Delete: “or (except to the extent that the presence of asbestos or contaminated material has been identified in the Contract Documents and/or any such material has been brought on to the site by the Contractor or any Contractor’s Person) compliance with clause 3.15.3 or with the Employer’s instructions under clause 3.15.4.” - After “Contract Documents” insert: - “or disclosed or provided to the Contractor in any reports or surveys prior to the Base Date” |
| - Clause 2.26.7 | - At clause 2.26.7.1 before “affects” insert: “directly and substantially”. In the hanging paragraph delete: “, or preventing the Contractor from, or delaying the Contractor in, securing such goods or materials or such services as are necessary for the proper carrying out of the Works.” |
| - Clause 2.26.8 | - Before “affects” insert: “directly and substantially”. - Delete “or” at the end of clause 2.26.8.2 and replace with “,”. - Delete clause 2.26.8.3. - Delete “, or in the case of guidance by the Construction Leadership Council or its successor”. - At the end of the clause insert: - “subject to the exercise of such power not being reasonably foreseeable to the Contractor at the Base Date”. |
| - Clause 2.26.9 | - At the end of the clause insert: “provided the Contractor has complied with clause 2.1.7”. |
| - Clause 2.29.1 | - Delete and substitute: - “Provided the Employer has issued a Non-Completion Notice for the Works or a Section, the Employer may, not later than 5 days before the final date for payment of the amount payable under clause 4.24 or (if applicable) 8.7.6, 8.8.3 or 8.12.5 give notice in writing to the Contractor in the terms set out in clause 2.29.2.” |
| - Clause 2.29.2 | - After “and the date of practical completion of the Works or that Section” insert (before the colon): - “or the date of termination of the Contractor’s employment under this Contract in accordance with clause 8 (whichever is the earlier)”. |
| - Clause 2.29.4 | - Delete “2.29.1.2” at both places where it appears, and substitute: “2.29.1”. |
|  | - After clause 2.35 insert new clauses 2.35A and 2.35B: |
| - “2.35A | - In cases of urgency the Employer may require any matter notified under clause 2.35 to be made good within such period of time specified by the Employer as the circumstances require. |
| - 2.35B | - Any works carried out by the Contractor under clause 2.35 or 2.35A must be carried out at a time to be approved by the Employer and the Contractor shall use all reasonable endeavours to eliminate any disruption to the Employer and/or any users of the completed Works and all remedial works shall be carried out causing as little damage and inconvenience as reasonably practicable and making good any physical damage so caused.” |
| - Clause 2.36 | - At the end insert: - “Provided that the Employer shall not be required to issue any Notice of Completion of Making Good any earlier than the expiry of the relevant Rectification Period”. |
| - Clause 2.37 | - Delete and substitute: |
| - “2.37.1 | - The Contractor, in addition to its obligations under the CDM Regulations in relation to the health and safety file, shall, before practical completion of the Works or relevant Section and without cost to the Employer, supply to the Employer: - .1 the Contractor’s Design Documents and related information; - .2 complete sets of records and as-built drawings (and electronic copies in a readable form if so requested) showing the buildings (plans, elevations and sections), the main lines of drainage and the services installations in the number of copies set out or referred to in the Contract Particulars; and - .3 complete sets of manufacturers’ product information documents, installation instructions, operation and maintenance manuals and other relevant literature in the number of copies set out or referred to in the Contract Particulars. |
| - 2.37.2 | - Between six and eight weeks before the anticipated date of practical completion of the Works or any Section, the Employer and the Contractor shall meet to agree the precise list of documents and information which the Employer requires the Contractor to provide under clause 2.37.1.” |
| - Clause 2.38 | - Delete and substitute: |
| - “2.38.1 | - Subject to any rights in any designs, drawings and other documents supplied to the Contractor for the purposes of this Contract by or on behalf of the Employer, the Intellectual Property in all Contractor’s Design Documents shall remain vested in the Contractor. |
| - 2.38.2 | - The Contractor grants to the Employer, with immediate effect, an irrevocable, royalty-free, non-exclusive licence (to remain in full force and effect notwithstanding discharge, termination or disputes of or under this Contract) to use the Intellectual Property and to copy the Contractor’s Design Documents for any purpose relating to the Works including the construction, completion, maintenance, letting, sale, promotion, advertisement, reinstatement, refurbishment and repair of the Works. The licence shall carry the right to grant sub-licences and shall be transferable to third parties. The licence shall enable the Employer to use and reproduce the Contractor’s Design Documents for any extension of the Works, but shall not include a licence to reproduce the Intellectual Property in the Contractor’s Design Documents for any extension of the Works. |
| - 2.38.3 | - The Contractor shall have no liability for any use by the Employer of any of the Contractor’s Design Documents for any purpose other than that for which they were prepared. |
| - 2.38.4 | - The Contractor shall not grant to any third party the right to use any of the Contractor’s Design Documents or any Intellectual Property in any of the Contractor’s Design Documents except under any third party rights or collateral warranty it is obliged to give under this Contract. |
| - 2.38.5 | - The Contractor warrants that the Contractor’s Design Documents (except to the extent that duly authorised sub-contractors or consultants (including the Novating Consultants if any) are used) are the Contractor’s own original work and that in any event their use in connection with the Works shall not infringe the rights of any third party. The Contractor further warrants that where duly authorised sub-contractors or consultants (including the Novating Consultants if any) are used their work shall be original and shall be covered by the licence granted to the Employer under clause 2.38.2. |
| - 2.38.6 | - The Contractor shall: .1 keep electronic copies of the Contractor’s Design Documents and any other documents required to be prepared or obtained by the Contractor under this Contract in a readable form for a period of 6 years from practical completion of the Works; and - .2 on reasonable request at any time and following reasonable prior written notice give to the Employer, or those authorised by the Employer, access to such documents and to provide copies (including electronic and digital copies in a readable form) of such documents at the Employer’s expense. |
| - 2.38.7 | - The Contractor waives any moral rights in the Contractor’s Design Documents or in relation to the Works that it may have under Part 1 Chapter IV of the Copyright, Designs and Patents Act 1988 or any re-enactment or modification of it and will procure a written waiver in equivalent terms from its employees, its sub-contractors and its sub-contractors’ employees.” |

| - Section 3 | - Control of the Works |
| --- | --- |
|  | - After clause 3.3.2 insert new clauses 3.3.3 and 3.3.4: |
| - “3.3.3 | - Where the Employer has consented to the Contractor sub-contracting the design of all or any portion of the Works, the Contractor shall not afterwards terminate the employment of, or substitute, any person, firm or company retained in respect of such design without the prior written consent of the Employer. |
| - 3.3.4 | - The Contractor shall not alter, waive, vary, or depart from any terms of a sub-contract or appointment entered into with a Sub-Contractor without the Employer’s prior written consent.” |
| - Clause 3.4.1 | - In line 2 after “the Contractor’s employment under this Contract”, insert: - “and the Contractor shall notify the Employer and the Employer’s Agent if it appoints a Sub-Contractor using a different form of sub-contract and shall, on request, provide a full copy of that different form of sub-contract to the Employer and/or Employer’s Agent.” |
| - 3.4.2.5 | - Delete “the Rights Particulars provide" and replace with: - “this Contract provides”. |
|  | - Add a new sub-clause 3.4.2.6 |
| - “3.4.2.6 | - that each party to the sub-contract shall co-operate and collaborate with the Employer and the Building Safety Regulator.” |
| - Clause 3.5.1 | - At the end of the sub-clause insert: - “within 3 Business Days of its receipt”. |
| - Clause 3.8 | - Delete the second sentence and substitute: “The Contractor shall, notwithstanding such request, comply with that instruction. Unless it is subsequently decided in any proceedings that the provision specified by the Employer in answer to the Contractor’s request does not empower the issue of that instruction then its issue shall be treated for all the purposes of this Contract as empowered by the provision of the Conditions so specified by the Employer.” |
| - Clause 3.13.1 | - After “site of” insert: “or rectification of”. |
| - Clause 3.16 | - Add new clauses 3.16.5 to 3.16.7: - “.5 the Contractor confirms that is has the skills, knowledge and experience and, where the Contractor is not an individual the organisational capability, to fulfil the relevant requirements applicable to its role(s) under the CDM Regulations and in accordance with applicable standards. |
|  | - .6 whether or not the Contractor is the Principal Contractor or Principal Designer, compliance with this clause shall be at no cost to the Employer and shall not entitle the Contractor to an extension of time. |
|  | - .7 if the Employer appoints a replacement Principal Designer or Principal Contractor, the Employer shall immediately upon that appointment notify the Contractor with details of the new appointee.” |
|  | Insert new clause 3.17: |
| - 3.17 | In respect of its obligations under Part 2A of the Building Regulations: |
| - 3.17.1 | the Contractor confirms that it: .1 has the skills, knowledge, experience and behaviour and, where the Contractor is not an individual the organisational capability, to fulfil the relevant competency requirements applicable to its role(s) and in accordance with applicable standards; and .2 will notify the Employer where at any time it ceases to satisfy these competency requirements; and - .3 will within 28 days of ceasing to be appointed as the Principal Designer and/or the Principal Contractor provide a document to the Employer explaining the arrangements it had put in place to comply with its role as the Principal Designer and/or the Principal Contractor. |
| - 3.17.2 | whether or not the Contractor is the Principal Contractor or Principal Designer, compliance with this clause shall be at no cost to the Employer and shall not entitle the Contractor to an extension of time; and |
| - 3.17.3 | if the Employer appoints a replacement Principal Designer or Principal Contractor, the Employer shall immediately upon that appointment notify the Contractor with details of the new appointee.” |

| - Section 4 | - Payment |
| --- | --- |
| - Clause 4.4.1 | - Delete clause 4.4.1 and substitute: - “The Contract Sum is exclusive of VAT and, in relation to each payment to the Contractor for any supply made under this Contract: - .1 the Contractor shall within two Business Days following the issue by the Employer of a Payment Notice issue to the Employer an appropriate VAT invoice in respect of such supply, indicating whether or not the reverse charge applies to the supply; and - .2 subject to the Contractor complying with clause 4.4.1.1 and unless the reverse charge applies, the Employer shall in addition pay to the Contractor the amount of any VAT properly chargeable in respect of such supply.” |
| - Clauses 4.4.3 to 4.4.5 | - Insert new clauses 4.4.3 to 4.4.5: - “4.4.3 The Contractor shall include within each Interim Payment Application a request for the Employer to confirm in writing whether the reverse charge applies to the supply to which the Interim Payment Application relates. The Employer shall provide such confirmation with, or not later than the issue of, the Payment Notice relating to such supply. - 4.4.4 If the paying party for the final payment under clause 4.8 is the Employer, the Contractor shall not later than the due date fixed under clause 4.24.5 request the Employer to confirm in writing whether the reverse charge applies to the supply to which the final payment relates. The Employer shall provide such confirmation with, or not later than the issue of, the Final Payment Notice. - 4.4.5 The Employer is registered for VAT in the United Kingdom under the registration number stated in the Contract Particulars.” |
| - Clause 4.7.1 | - After “made by the Employer to the Contractor” insert: - “or the Contractor to the Employer, as the case may be,”. |
| - Clause 4.9.1 | - Delete “14” and substitute: “21”. |
| - Clause 4.10.4 | - Delete “The Employer’s fiduciary interest in the Retention referred to in clause 4.16 shall not prevent the Employer from exercising” and substitute: - “The Employer may exercise”. |
| - Clause 4.11.3 | - In line 2 delete “or on request”. At the end of the clause insert: - “The Contractor shall, on request, submit such further details as are reasonably requested by or on behalf of the Employer.” |
| - Clause 4.16.1 and 4.16.2 | - Delete sub-clauses 4.16.1 and 4.16.2 and substitute: |  |
| - “4.16.1 | - the Employer’s interest in the Retention shall not be fiduciary, either as trustee for the Contractor or otherwise; |
| - 4.16.2 | - the relationship of the Employer and the Contractor with regard to the Retention shall be solely that of debtor and unsecured creditor, as set out in clause 4.16; |
| - 4.16.3 | - the Employer shall have no obligation to invest the Retention or any part of it; |
| - 4.16.4 | - the Employer shall have no obligation to segregate the Retention or any part of it in a separate banking account, or in any other manner whatsoever; |
| - 4.16.5 | - the Employer shall be entitled to the full beneficial interest in the Retention and every part of it (and its interest and any income arising from it) unless and until the Retention is paid to the Contractor pursuant to this Contract.” |
|  | - Insert a new clause 4.19.3: |
| - “4.19.3 | - The Contractor shall not be entitled to any loss and/or expense on account of any circumstance that arises due to any error, omission, negligence or default of the Contractor or any of the Contractor’s Persons.” |
|  | Insert new clauses 4.20.5 and 4.20.6: |
| - “4.20.5 | - The Contractor shall use its best endeavours to prevent or minimise any disruption to the regular progress of the Works and each Section and to mitigate any loss and/or expense incurred by it. |
| - 4.20.6 | - The Contractor shall not be entitled to recover any direct loss and/or expense resulting from any delay in the regular progress of the Works or any part caused by a Relevant Matter where such delay is concurrent with another delay for which the Contractor is responsible.” |
| - 4.21.3 | - Delete: or (except to the extent that the presence of asbestos or contaminated materials has been identified in the Contract Documents and/or any such material has been brought on to the site by the Contractor or the Contractors Person) compliance with clause 3.15.3 or with Architect/Contract Administrator’s instructions under clause 3.15.4.” |
| - Clause 4.24.1 | - Delete “Following” and substitute: “Within 1 month of”. |
| - Clause 4.24.3 | - In line 1 delete “3” and substitute: “1”. - In line three delete “2” and substitute: “1”. |
| - Clause 4.24.4 | - In line 2 delete “2” and substitute: “1”. |
| - Clause 4.24.5 | - At the beginning of the clause, delete “The” and substitute: - “Where the Final Statement shows a payment due from the Employer to the Contractor, the”. - Insert a new paragraph after 4.24.5.3: - “Where the Final Statement shows a payment due from the Contractor to the Employer, the due date for the final payment shall be one month after the date of submission to the other Party of the Final Statement.” |

| - Section 5 | - Changes |
| --- | --- |
| - [Clause 5.1.3 | - Change the full stop at the end of sub-clause 5.1.2.4 to a semicolon and add a new sub-clause 5.1.3: - “.3 without prejudice to the rest of clause 5.1, an instruction from the Employer supplementing or amending the Third Party Agreements.”] |
| - Clause 5.6 | - At the end of the clause, before the full stop, insert: - “provided always that the substantial change in the conditions is not caused by any error, omission, negligence or default of the Contractor or the Contractor’s Persons”. |

| - Section 6 |  | - Injury, Damage and Insurance |
| --- | --- | --- |
| - Clause 6.1 |  | - In line 3, after “or caused by the carrying out of the Works” insert: - “or of any other obligation of the Contractor under this Contract”. |
| - Clause 6.2 |  | - In line 4, after “Works”, insert: - “or in the performance of any other obligation of the Contractor under this Contract”. |
| - Clause 6.3A |  | - After clause 6.3 insert a new clause 6.3A: |
| - “Trespass and Nuisance |  |  |
| - 6.3A.1 |  | - The Contractor shall at all times take reasonable safety and other measures to prevent any trespass, public or private nuisance (including caused by noxious fumes, noisy working operations, oversailing or material or debris on the public highway) or other unlawful interference with the rights and activities of any nearby landowner, tenant or occupier or any Statutory Provider arising out of the carrying out of the Works. The Contractor shall assist the Employer in defending any relevant action or proceedings which may be instituted. |
| - 6.3A.2 |  | - The Contractor shall be responsible for and shall indemnify the Employer from and against any and all expenses, liabilities, losses, claims and proceedings whatsoever resulting from any such trespass, nuisance or interference. |
| - 6.3A.3 | - The Employer may issue to the Contractor such instructions as the Employer considers necessary if any injunction is granted or Court order is made in consequence of any such trespass, nuisance or interference. Except as described above, the Contractor shall not be entitled to any additional payment (whether by way of an addition to the Contract Sum or otherwise) nor to an extension of time due to any instruction referred to in this sub-clause. |  |  |
| - 6.3A.4 |  | - If carrying out the Works or any obligation pursuant to this Contract would otherwise be an act of trespass, public or private nuisance as described above, the Contractor shall, at no cost to the Employer, obtain the prior written agreement of the owners or occupiers of any adjoining or neighbouring property to that act. That agreement shall be subject to the Employer’s approval before its completion. The Contractor shall comply with any condition or obligation contained in that agreement, at no cost to the Employer and shall not be entitled to any extension of time as a result of any condition or obligation contained in that agreement.” |
| - Clause 6.5.1 |  | - Delete in line 1 “Employer’s Requirements” and substitute: “Contract Particulars”. - Delete in lines 1-2 “in the names of the Employer and the Contractor” and insert: - “in the joint names of the Employer, the Contractor [and such other parties identified in the Contract Particulars]”. |
| - Clause 6.8 |  | - In the definition of “Joint Names Policy” after “the Employer and the Contractor” insert: - “and such other persons as the Employer shall notify to the Contractor”. |
| - Clause 6.9.1 |  | - At the end of the clause insert: - “The Contractor (at the Employer’s request from time to time) shall ensure, where Insurance Option A applies, and the Employer may arrange, where Insurance Option B or C applies, that the Joint Names Policy referred to in paragraph A.1, B.1, C.1 or C.2 of Schedule 3 shall provide for recognition of such additional persons as the Employer may reasonably require (including each Funder, Purchaser and Tenant) as an insured under the relevant Joint Names Policy”. |
| - Clause 6.15 |  | - Renumber clause 6.15 as clause 6.15.1 and its sub-clauses as 6.15.1.1 to 6.15.1.3. |
| - Clause 6.15.1.3 |  | - Insert at the end of clause 6.15.1.3: - “by way of an original letter from the Contractor’s insurers or brokers confirming the Contractor’s then current professional indemnity insurance (including any sub-limits) and that the premiums for that insurance have been paid in full at the date of that letter”. |
| - Clause 6.15.2 |  | - Insert new clauses 6.15.2 to 6.15.5: |
| “6.15.2 |  | - The Contractor shall maintain that professional indemnity insurance: - .1 with reputable insurers authorised to carry on insurance business in United Kingdom; and - .2 on terms that do not require the Contractor to discharge any liability before being entitled to recover from the insurers and that would not adversely affect the rights of any person to recover from the insurers under the Third Parties (Rights Against Insurers) Act 2010. |
| - 6.15.3 |  | - Such insurance shall cover (amongst other things) all the Contractor’s liability under this Contract in respect of defects or insufficiency in design, upon customary and usual terms and conditions prevailing for the time being in the insurance market. |
| - 6.15.4 |  | - The Contractor shall not, without the prior approval in writing of the Employer, settle or compromise with the insurers any claim which the Contractor may have against the insurers and which relates to a claim by the Employer against the Contractor, or by any act or omission lose or prejudice the Contractor’s right to make or proceed with such a claim against the insurers. Any increased or additional premium required by insurers due to the Contractor’s own claims record or other acts, omissions, matters or things particular to the Contractor shall be treated as within commercially reasonable rates. |
| - 6.15.5 |  | - The obligations contained in clauses 6.15 and 6.16 in respect of professional indemnity insurance shall continue notwithstanding discharge, termination or disputes under this Contract.” |
| - Clause 6.16 |  | - Delete and substitute: - “If the insurance referred to in clause 6.15 is not available to the Contractor at commercially reasonable rates and terms (excluding any premiums attributable to the actions, omissions, errors or defaults of the Contractor), the Parties shall meet and the Contractor shall outline the steps it intends to take to manage the insured risks. The Contractor shall fully co-operate with any measures reasonably required by the Employer, including: - .1 completing any proposals for insurance and associated documents; and - .2 maintaining such insurance at rates above commercially reasonably rates if the Employer undertakes in writing to reimburse the Contractor in respect of the net cost of such insurance to the Contractor above commercially reasonable rates.” |
|  |  | - After clause 6.16 insert new clauses 6.16A to 6.16B: |
| - “6.16A |  | - If the Contractor has not provided evidence of any policies required under this Contract to the Employer at tender stage, the Contractor shall provide it immediately after the execution of this Contract. In the event that in the Employer’s reasonable opinion those policies do not effect proper cover in accordance with this Contract, the Employer may require the Contractor to effect and the Contractor shall effect such further insurance as the Employer may reasonably require. |
| - 6.16B |  | - The Contractor shall procure that the Sub-Contractors shall maintain professional indemnity insurance as set out in the required form of Sub-Contractor’s deed of collateral warranty. Within 10 Business Days of the appointment of a Sub-Contractor, the Contractor shall procure and shall send to the Employer evidence that the Sub-Contractor’s insurance referred to in this clause is in force, including, if required by the Employer, an original letter from each Sub-Contractor’s insurers or brokers confirming: - .1 the Sub-Contractor’s then current insurance (including any sub-limits), as referred to in this clause; and - .2 that the premiums for that insurance have been paid in full at the date of that letter.” |

| - Section 7 | - Assignment, Performance Bonds and Guarantees, Third Party Rights and Collateral Warranties |
| --- | --- |
| - Clause 7.1 | - Delete and substitute: |
|  | “The Employer may, without the consent of the Contractor, assign the benefit of this Contract on not more than two occasions, and afterwards only with the consent of the Contractor; provided that an assignment to any Associate of the Employer or any assignment (whether by legal assignment, equitable assignment, charge or otherwise and including re-assignments) to and from any Funder shall also be permitted without consent and shall not count towards the number of assignments permitted without consent under clause 7.1.” |
| - Clause 7.2 | - Delete and substitute: |
|  | - “The Contractor shall not assign or charge the benefit of this Contract nor any right arising under it without the Employer’s prior written consent, which the Employer may withhold at its absolute discretion.” |
| - Clause 7.3 | - In clause 7.3.1, after “approved by the Employer” insert: - “at the Employer’s absolute discretion”. - In clause 7.3.2, at the end insert: - “or approved by the Employer at the Employer’s absolute discretion”. - At the end of clause 7.3, insert: - “or such other form as the Employer, in its absolute discretion, may approve.” - [Insert at the end: - “The Employer shall not be obliged to make any payment to the Contractor in connection with the Works until the Contractor has provided to the Employer any performance bond or guarantee required to be provided under this clause.”] |
| - Clauses 7.4 to 7.12 | - Delete clauses 7.4 to 7.11 and substitute new clauses 7.4 to clause 7.12: |
|  | - “Contractor Third Party Rights and Collateral Warranties |
| - 7.4 | - Unless the Employer has already served upon the Contractor a Nominating Notice in respect of the relevant Third Party, the Contractor shall within 14 days of a written request from the Employer identifying the relevant Third Party and its interest in the Works execute and deliver to the Employer a deed of collateral warranty in favour of the Third Party in the appropriate form set out in Part 4 of Schedule 7. |
| - 7.5 | - Except where the Contractor has already executed and delivered to the Employer a deed of collateral warranty in favour of the relevant Third Party in accordance with clause 7.4, the Employer (or its solicitors on its behalf) may from time to time serve a Nominating Notice upon the Contractor vesting the Third Party Rights upon a Third Party. |
| - 7.6 | - From the date of receipt by the Contractor of the Nominating Notice the Third Party Rights shall vest in the Third Party named in the Nominating Notice and such third party shall be entitled to enforce the Third Party Rights under the Contracts (Rights of Third Parties) Act 1999. |
| - 7.7 | - Where Third Party Rights have vested in a Third Party under clause 7.6, the Employer and the Contractor shall not be entitled without the consent of that Third Party to amend or vary the express provisions of clauses 7.5, 7.6 or 7.7 or the Third Party Rights vested in the Third Party but, subject to that, the rights of the Employer and the Contractor: - 7.7.1 to terminate the Contractor’s employment under this Contract (whether under section 8 or otherwise), or to agree to rescind this Contract; - 7.7.2 to agree to amend or otherwise vary or to waive any terms of this Contract; - 7.7.3 to agree to settle any dispute or other matter arising out of or in connection with this Contract, in each case in or on such terms as they shall in their absolute discretion think fit, - shall not be subject to the consent of any Third Party. |
| - 7.8 | - The Employer acknowledges that the Contractor shall not be in breach of this Contract by complying with the obligations imposed by any step-in rights conferred on a Third Party by the Third Party Rights. |
|  | - Contractor’s Design Team and Sub-Contractor Collateral Warranties |
| - 7.9 | - The Contractor shall within 7 days of the appointment of each Sub-Contractor and each member of the Contractor’s Design Team procure that the relevant parties execute and deliver to the Employer: - 7.9.1 a certified copy of the relevant sub-contract or appointment (the Contractor may redact particulars of the sub-contract sum or consultant’s fee); and - 7.9.2 a deed of collateral warranty from the Sub-Contractor or member of the Contractor’s Design Team in favour of the Employer in the form set out in Part 6 or 7 of Schedule 7 (as appropriate) with such amendments as may be approved by the Employer. |
| - 7.10 | - Unless a Nominating Notice in respect of the Third Party has already been served under a collateral warranty issued under clause 7.9, the Contractor shall within 21 days of a written request from the Employer identifying the relevant Third Party and its interest in the Works, procure that each Sub-Contractor and each member of the Contractor’s Design Team shall provide to the Employer a collateral warranty in favour of that Third Party in the form set out in Part 6 or Part 7 of Schedule 7 (as appropriate) with such amendments as may be approved by the Employer. |
| - 7.11 | - If the Contractor fails to provide any collateral warranty required by clause 7.10 the Employer may deduct and withhold from any monies otherwise due to the Contractor the amount stated in the Contract Particulars for each collateral warranty. These monies may be withheld until the required collateral warranty is provided and notwithstanding the carrying out of or the completion of the Works. |
| - 7.12 | - The obligations contained in clause 7 shall continue notwithstanding termination of this Contract, or determination of the Contractor’s employment under this Contract, for any reason whatsoever, including breach by the Employer.” |

| - Section 8 | - Termination |
| --- | --- |
| - Clause 8.4.1.3 | - After “remove” in line 2 insert: “or rectify”. |
| - Clause 8.4.1.5 | - After “clause 3.16” insert: “or 3.17”. |
| - Clause 8.5.1 | ## After “Insolvent” in line 1, delete the comma and insert: ## “then such event shall constitute a default and breach by the Contractor of this Contract and”. |
| - Clause 8.6 | ## In the heading delete “regulation 73(1)(b) of the PC Regulations” and replace with: ## “sections 78(2)(b) and 78(2)(c) of the Procurement Act 2023.” ## Renumber the existing clause 8.6 as clause 8.6.2. In that re-numbered clause delete from “or any person employed by it or acting on its behalf” to the end of the clause and insert: - “or any of its Associated Persons are in breach of clause 8.6.1 or, where the Employer is a Local or Public Authority, the Contractor or any of its Associated Persons shall have given any fee or reward the receipt of which is an offence under sub-section (2) of section 117 of the Local Government Act 1972 or, where this Contract is one to which section 78 of the Procurement Act 2023 applies, the circumstances set out in sections 78(2)(b) and 78(2)(c) of the Procurement Act 2023 apply and the Employer has complied with the relevant requirements of section 78.” |
| - Clause 8.6.1 | ## Insert a new clause 8.6.1: |
| - “8.6.1 | ## The Contractor shall, and shall procure that its Associated Persons shall: ### .1 not commit any act or omission which causes or could cause it or the Employer to breach, or commit an offence under, any laws relating to anti-bribery and/or anti-corruption; ### .2 comply with the Anti-Corruption Policy; ### .3 keep accurate and up to date records showing all payments made and received and all other advantages given and received by it in connection with this Contract and the steps it takes to comply with clause 8.6.1, and permit the Employer to inspect those records as reasonably required; ### .4 promptly notify the Employer of: ##### .i any request or demand for any financial or other advantage received by it; and ##### .ii any financial or other advantage it gives or intends to give ##### whether directly or indirectly in connection with this Contract; - and promptly notify the Employer of any breach of clause 8.6.1 either by itself or an Associated Person.” |
| - Clause 8.7.3A | ## After clause 8.7.3, insert a new clause 8.7.3A: ## “the Employer may, at any time after the date that the Contractor’s employment is terminated, claim against the Contractor [and the provider of any performance bond securing the Contractor’s performance under this Contract] for the Employer’s losses arising as a result of the termination, which losses shall be determined and become payable in accordance with clauses 8.7.4 and 8.7.5;”. |
| - Clause 8.7.6.1 | ## At the end of the clause (before the semi-colon) insert: ## “including any liquidated damages payable under clause 2.29.2” |
| - Clause 8.9.1.2 | ## Delete and insert: “Not used”. |
| - Clause 8.9.1.3 | ## After “clause 3.16” insert: “or 3.17”. |
| - Clause 8.9.4 | ## In line 1 delete “for any reason” and insert: ## “accrues the right to give a further notice to terminate its employment under clause 8.9.3, but”. ## In line 1-2 delete “clause 8.9.3 but” and insert: ## “that clause and”. |
| - Clause 8.11 | ## In the heading immediately before clause 8.11 and in the heading of clause 8.11 delete “regulation 73(1)(a) of the PC Regulations” and replace with: ## “section 78(2)(a) of the Procurement Act 2023.” |
| - Section 9 | - Settlement of Disputes |
|  | - Insert a new clause 9.3.3: |
| - “9.3.3 | the Adjudicator shall give written reasons with their decision”. |

| - Schedules |  |
| --- | --- |
| - Schedule 2 | - In Part 1 paragraph 1, delete sub-paragraph 1.4.2 and substitute: - “such completion shall not be treated as a Change.” - Delete sub-paragraph 1.4.3. |
| - Schedule 5 | - Delete and insert: “Not used”. |
| - Schedule 6 | - Delete and insert: “Not used”. |
| - Schedule 7 | - Insert new attached Schedule 7, which comprises: - [Part 1: Novation Agreement] - [Part 2: Performance Bond] - [Part 3: Parent Company Guarantee] - Part 4: Contractor’s Collateral Warranty - Part 5: Third Party Rights - [Part 6: Contractor’s Design Team’s Collateral Warranty] - Part 7: Sub-Contractor’s Collateral Warranty |
|  | Insert new Schedule 8: |
| - [Schedule 8 | - Contract Documents List] |

- THIS DOCUMENT is executed as a deed in duplicate and delivered on the date stated at the beginning of this Deed.

SCHEDULE 7

# PART 1: NOVATION AGREEMENT

- Dated: 2026 - [CONSULTANT] - [EMPLOYER] - [CONTRACTOR]

Novation Agreement

relating to [DETAILS]

- THIS AGREEMENT is made on 2026

- BETWEEN:

- [CONSULTANT] [(registered number [NUMBER]) whose registered office is at] [of] [ADDRESS] (“the Consultant”);

- [EMPLOYER] [(registered number [NUMBER]) whose registered office is at] [of] [ADDRESS] (“the Employer”); and

- [CONTRACTOR] [(registered number [NUMBER]) whose registered office is at] [of] [ADDRESS] (“the Contractor”).

- BACKGROUND:

- The Employer appointed the Consultant under an appointment dated [DATE] (“the Appointment”) to provide consultancy services (“the Services”) for the development [DESCRIBE INCLUDING LOCATION] (“the Project”).

- The Employer and the Contractor have entered into a building contract for the design and construction of the Project.

- The parties have agreed to novate the Appointment from the Employer and the Consultant to the Contractor and the Consultant; and the Employer wishes to be discharged from its obligations under the Appointment.

- OPERATIVE CLAUSES:

- CONSIDERATION

- This Agreement is made in consideration of the payment of one pound (£1.00) by the Contractor to the Employer, receipt of which the Employer acknowledges.

- NOVATION OF APPOINTMENT AND SUBSTITUTION OF CONTRACTOR

  - This Agreement novates the Appointment from the Employer and the Consultant to the Contractor and the Consultant. From the date of this Agreement, the Contractor will substitute and replace the Employer as employer under the Appointment.

  - The Appointment will take effect as if the same had been entered into originally between the Contractor and the Consultant. Subject to the terms of this Agreement, the Appointment will remain in full force and effect.

- RELEASE AND DISCHARGE OF EMPLOYER

- The Consultant releases and discharges the Employer from any and all obligations and liabilities owed to the Consultant under the Appointment. The Consultant agrees that it will make no further claims against the Employer under and arising out of the Appointment.

- RELEASE AND DISCHARGE OF CONSULTANT

- Subject to the Consultant providing a collateral warranty to the Employer in accordance with clause 9 and without prejudice to the Employer’s rights under that collateral warranty, the Employer releases and discharges the Consultant from any and all obligations and liabilities owed to the Employer under the Appointment.

- CONTRACTOR’S UNDERTAKING

- The Contractor undertakes with the Employer and the Consultant to perform the Appointment and be bound by its terms as if the Contractor had been a party to the Appointment from the commencement of the Services instead of the Employer.

- CONSULTANT’S WARRANTIES

  - The Consultant warrants to the Contractor that it has performed and will continue to perform and be bound by the terms and obligations of the Appointment.

  - The Consultant acknowledges that the Contractor has relied upon, and will rely upon, the Consultant’s performance of the terms and obligations in the Appointment before, during and after the date of this Agreement.

  - The Consultant confirms that it will be liable for all loss or damage suffered or incurred by the Contractor as a result of any breach of the Appointment, irrespective of whether such losses were also suffered or incurred by the Employer (whether solely, or jointly with the Contractor, or otherwise) and irrespective of whether such loss or damage was suffered or incurred prior to the date of this Agreement.

- RIGHTS OF ACTION

  - All rights of action and remedies vested or which may vest in the Consultant arising from the Appointment, will be brought against the Contractor from the date of this Agreement.

  - All rights of action and remedies vested or which may vest in the Employer arising from the Appointment, will vest in the Contractor from the date of this Agreement.

- WARRANTY AS TO FEES

- The Consultant acknowledges that all fees, disbursements and expenses due to the Consultant under the Appointment [to the date of this Agreement have been paid in full by the Employer] [set out in Schedule 1 have been paid by the Employer]. The Employer agrees that such fees, disbursements and expenses are not repayable by the Contractor to the Employer.

- DEED OF COLLATERAL WARRANTY

- The Consultant will enter into a deed of collateral warranty in favour of the Employer in the form of the draft at Schedule 2.

- THIRD PARTY RIGHTS

- The parties do not intend that any term of this Agreement will be enforceable by any person under the Contracts (Rights of Third Parties) Act 1999.

- GOVERNING LAW AND JURISDICTION

  - This Agreement and any non-contractual obligations arising out of or in connection with it will be governed by English Law.

  - The parties agree that the courts of England and Wales have exclusive jurisdiction to determine any dispute arising out of or in connection with this Agreement (including, without limitation, in relation to any non-contractual obligations).

- COUNTERPARTS

- This Agreement may be executed in any number of counterparts, each of which will constitute an original, but which will together constitute one agreement.

- SCHEDULE 1

Fees Paid To Date

- SCHEDULE 2

Form Of Collateral Warranty

- The collateral warranty will be the same form as the collateral warranty contained in Schedule [INSERT] of the Appointment.

- THIS DOCUMENT is executed as a deed and delivered on the date stated at the beginning of this Deed.

# SCHEDULE 7

# [PART 2: PERFORMANCE BOND]

| Dated: 2026 - [CONTRACTOR] - [SURETY] - [EMPLOYER] |  |
| --- | --- |
| Retention bond |  |
| relating to [DETAILS] |  |

CONTENTS

Clause	Page

1	CONSIDERATION	1

2	GUARANTEE	1

3	BOND AMOUNT	1

4	PROCEDURAL CONDITIONS	2

5	NO DISCHARGE OF LIABILITY	2

6	EXPIRY	2

7	CONTRACTOR’S UNDERTAKING	2

8	DEFENCE AND COUNTERCLAIM	3

9	THIRD PARTY RIGHTS	3

10	ASSIGNMENT	3

11	INTERPRETATION	3

12	JURISDICTION	3

THIS BOND is made on			2026

PARTIES:

- [NAME] [([registered number [number])] whose registered office is at] [of]  [Address] (“the Contractor”); and

- [NAME] [([registered number [number])] whose registered office is at] [of]  [Address] (“the Surety”); and

- [NAME] [([registered number [number])] whose registered office is at] [of]  [Address] (“the Employer”, which expression shall include its successors and assigns).

BACKGROUND:

- By a contract dated [date] and entered into between the Employer and the Contractor (“the Building Contract”), particulars of which are set out in Schedule 1 to the Bond (“the Schedule”), the Contractor has agreed with the Employer to execute works (“the Works”) upon and subject to the terms and conditions set out within the Building Contract.

The Employer has agreed, at the request of the Contractor, that he will not exercise his rights under the terms of the Building Contract to deduct the Retention as defined in the Building Contract from amounts otherwise payable to the Contractor.

The Surety has agreed with the Employer, at the request of the Contractor, to guarantee the sum of money set out in the Schedule upon the terms and conditions of this Bond subject to the limitation set out in clause 3.

IT IS AGREED AS FOLLOWS:

- CONSIDERATION

This Bond has been entered into in consideration of the payment to the Contractor of the Contract Sum (as defined in the Building Contract) or parts of the same without any deduction of Retention by the Employer.

- GUARANTEE

The Surety guarantees unconditionally and irrevocably to the Employer that within 7 days of receipt of the Employer’s first written demand for payment complying with clause 4, the Surety shall, subject to the provisions of this Bond, pay to the Employer amounts up to the Bond Amount.

The Surety agrees that the Employer may submit more than one demand for payment provided that the aggregate amount claimed by the Employer in all demands does not exceed the Bond Amount.

A demand under clause 2.1 shall, for the purposes of this Bond but not further or otherwise, be conclusive evidence (and admissible as such) that the amount demanded is properly due and payable to the Employer by the Contractor.

Furthermore, except as set out in clause 4, the Surety waives all rights of objection and defence to the demand of the Employer, except in the case of a fraudulent demand or where the amounts set out in a demand exceed the Bond Amount.

BOND AMOUNT

The maximum aggregate liability of the Surety or the Contractor under this Bond shall not exceed the Bond Amount.

The Bond Amount shall, after receipt by the Surety of the Employer’s written notice confirming the date of issue of the next [Interim Certificate][Payment Notice] following Practical Completion in accordance with the Building Contract, reduce by one half until the Expiry Date.

PROCEDURAL CONDITIONS

Any demand by the Employer under clause 2 shall:

be refer to this Bond and be addressed to the Surety at its office as referred to in this Bond;

state the amount of the Retention that would have been held by the Employer in accordance with the Building Contract at the date of the demand had Retention been deducted; and

state the amount demanded under this Bond which, together with any amounts previously demanded and paid, shall not exceed the amount stated in clause 3.

The Employer shall not be obliged before issuing any demand under clause 2 to take any action or any proceedings against or to make any claim in the insolvency of the Contractor.

NO DISCHARGE OF LIABILITY

The Surety shall not be discharged or released by:

any fact, event or rule of law which, but for clause 5 might operate to release in whole or in part the Surety from its obligations under this Bond including (without limitation) any alteration, variation or waiver of any of the terms conditions and provisions of the Building Contract or in the extent or nature of the Works and no allowance of time by the Employer under or in respect of the Building Contract or the Works on the part of the Employer shall in any way release reduce or affect the liability of the Surety under this Bond;

any fact event or rule of law which results in any total or partial invalidity, illegality or unenforceability of the Building Contract which the Contractor could have avoided by the use of its reasonable endeavours or could by using its reasonable endeavours have drawn to the attention of the Employer prior to the date of the Building Contract (in which case for the purposes of this Bond the Building Contract will be deemed valid, legal and enforceable as if such reasonable endeavours had been exercised and appropriate steps been taken to avoid or mitigate the invalidity, illegality or unenforceability); or

a legal limitation, disability or incapacity of the Contractor.

EXPIRY

Whether or not this Bond shall be returned to the Surety the obligations of the Surety under this Bond shall be released and discharged absolutely upon the Expiry Date (as defined in the Schedule) except in respect of any demand which has been made upon the Surety on or before the Expiry Date.

CONTRACTOR’S UNDERTAKING

The Contractor, having requested the execution of this Bond by the Surety, undertakes to the Surety (without limitation of any other rights and remedies of the Employer or the Surety against the Contractor) to perform and discharge the obligations on its part set out in or instructed under the Building Contract. Furthermore the Contractor undertakes to the Employer that he will not seek to recover from the Employer a sum due or to become due to the Contractor which has been taken into account when assessing sums due to the Employer under this Bond.

DEFENCE AND COUNTERCLAIM

All sums payable by the Surety to the Employer will be a debt and the Surety shall have no right of set-off or counterclaim against the Employer or any other person as would have been available to the Contractor under the Building Contract.

THIRD PARTY RIGHTS

No party who is not a party to this Bond shall be entitled to enforce any of its terms for his own benefit and the application of the Contracts (Rights of Third Parties) Act 1999 to the terms of this Bond are expressly excluded.

ASSIGNMENT

The benefit of this Bond may be assigned by the Employer at any time without the prior written consent of the Surety or the Contractor subject to the Employer giving written notice of such assignment to the Contractor and the Surety.

INTERPRETATION

In this Bond the words and expressions shall, unless otherwise provided,  have the meaning set out in the Building Contract.

JURISDICTION

The Bond shall be governed by and construed in accordance with the laws of England and Wales and be in all respects subject to the non-exclusive jurisdiction of the courts of England and Wales.

SCHEDULE 1

The Building Contract:	A contract [date] between the Employer and the Contractor in the form known as [name of standard form] for the [design,] construction and completion of works comprising [description of the works] for the original contract sum of £[figures] ([words] pounds)

The Bond Amount:	The sum of £[figures] ([words]) [exclusive of interest, legal fees and expenses]

The Expiry Date:		The date of the issue of the [Certificate][Notice] of Completion of Making Good Defects under the Building Contract which shall be conclusive for the purpose of this Bond.

THIS DOCUMENT is executed as a deed and delivered on the date stated at the beginning of this Deed.

[EXECUTION BY ALL PARTIES INCLUDING EMPLOYER]

SCHEDULE 7

[PART 3: PARENT COMPANY GUARANTEE]

# SCHEDULE 7

# PART 4: CONTRACTOR’S COLLATERAL WARRANTY

| - Dated: 2026 - [CONTRACTOR] - [BENEFICIARY] - [EMPLOYER] |  |
| --- | --- |
| Contractor warranty |
| relating to [SPECIFY] |

PARTICULARS

| Date of this Deed |  |
| --- | --- |
| The Contractor | [NAME][(registered number [NUMBER] [whose registered office is at] [of] [ADDRESS]. |
| The Beneficiary | [NAME][(registered number [NUMBER] [whose registered office is at] [of] [ADDRESS]. |
| The Beneficiary’s Interest | the Beneficiary is [providing finance in connection with the Project, whether that person acts on its own account, as agent for a syndicate of other parties or otherwise] [the/a] [landlord][freehold owner] [purchaser] [tenant] of [the Site] [DESCRIPTION OF PART OF THE SITE]. |
| The Employer | [NAME][(registered number [NUMBER] [whose registered office is at] [of] [ADDRESS]. |
| The Contract | the contract dated [DATE] made between the Contractor and the Employer. |
| The Works | the [design and] construction of the works to be provided by the Contractor under the Contract as detailed in the Contract. |
| The Project | the [DESCRIBE PROJECT] at the Site. |
| The Site | [DETAILS]. |
| Liability Period | the period from the date of the Contract until the date 12 years after the date of practical completion of the Works. |
| Professional Indemnity Insurance | professional indemnity insurance with a minimum limit of indemnity of not less than £[FIGURES] ([WORDS] million pounds) for any one occurrence or series of occurrences arising out of any one event. |
| [Notice Period | [28] days]. |
| [The Contractor’s Design Documents | all drawings, designs, charts, specifications, plans and any other documents or materials (including any computer software developed by the Contractor used to generate them and any designs contained in them) but excluding internal memoranda and documents, working papers and templates, which have been created and/or developed by the Contractor in the course of performing its obligations under the Contract.] |
| Termination Right | a right which may be or become available to the Contractor to terminate or treat as terminated or repudiated the Contract or its engagement under it or discontinue or suspend the performance of any duties or obligations under the Contract. |

THIS DEED is made on the date set out in the Particulars

- BETWEEN:

- The Contractor; [and]

- The Beneficiary; [and

- The Employer].

- BACKGROUND:

- The Employer has appointed the Contractor under the Contract to provide the Works in relation to the Project.

- The Beneficiary’s Interest in the Project is set out in the Particulars.

- The Contractor is obliged under the Contract to give a warranty in this form in favour of the Beneficiary.

- OPERATIVE PROVISIONS

- DEFINITIONS

- Subject to the words defined in the Particulars (which shall have that meaning throughout this Deed), the words defined in the Contract will have the same meaning in this Deed.

- CONSIDERATION

- This Deed is made in consideration of the payment of one pound (£1.00) by the Beneficiary to the Contractor receipt of which the Contractor acknowledges.

- CONTRACTOR’S DUTIES UNDER THE CONTRACT

- The Contractor warrants to the Beneficiary that it has performed and will continue to perform its duties under the Contract in accordance with the Contract and that it has exercised and will continue to exercise reasonable skill and care (or such higher duty as the Contract imposes) in relation to the following (so far as it is responsible for them):

  - the design of the Works;

  - the selection of goods, materials, equipment or plant for the Works; and

  - the satisfaction of any performance requirement or specification of or for the Works.

- INTELLECTUAL PROPERTY RIGHTS

  - Subject to the following provisions of this Deed, all Intellectual Property in the Contractor’s Design Documents will remain vested in the Contractor.

  - The Contractor grants (or, if such a grant cannot legally take place until a later date, agrees to grant) to the Beneficiary with effect from the date of this Deed or in the case of any of the Intellectual Property not yet in existence with effect from its creation, an irrevocable, royalty-free, non-exclusive licence.

  - Such licence will:

    - remain in full force and effect notwithstanding the completion of the Contractor’s obligations or the termination of the Contract or this Deed or the determination of the Contractor’s engagement under the Contract or any dispute under the Contract or this Deed;

    - allow the Beneficiary to use the Intellectual Property and to reproduce all Contractor’s Design Documents for any purpose whatsoever connected with the Project including, but without limitation, the execution, completion, maintenance, letting, advertisement, modification, reinstatement and repair of the Project;

    - carry the right to grant sub-licences and will be transferable to third parties; and

    - enable the Beneficiary to use and reproduce the Contractor’s Design Documents for any extension of the Project, but not include a licence to reproduce the Intellectual Property in the Contractor’s Design Documents for any extension of the Project.

  - The Contractor will not grant to any third party the right to use any of the Contractor’s Design Documents except under any warranty or third party rights it is obliged to give under the Contract or under this Deed or as otherwise required to enable it to fulfil its obligations under the Contract.

  - The Contractor will not be liable for any use the Beneficiary may make of the Contractor’s Design Documents for any purpose other than that for which they were prepared.

  - The Contractor warrants that the Contractor’s Design Documents (except to the extent that duly authorised sub-consultants have been used to prepare the same) are the Contractor’s own original work and that in any event their use in connection with the Project will not infringe the rights of any third party. The Contractor further warrants that where duly authorised sub-contractors are used their work will be original and that their work will be covered by the licence granted to the Beneficiary under clause 4.2.

  - The Contractor will:

keep electronic copies of the Contractor’s Design Documents and any other documents required to be prepared or obtained by the Contractor under the Contract  in a readable form for a period of 6 years from practical completion of the Works; and

on reasonable request at any time and following reasonable prior notice to give to the Beneficiary, or anyone authorised by the Beneficiary, access to such documents and to provide copies (including electronic copies in a readable form) of such documents at the Beneficiary’s expense.

  - The Contractor waives any moral rights in the Contractor’s Design Documents or in relation to the Works that it may have under Part 1 Chapter IV of the Copyright, Designs and Patents Act 1988 or any re-enactment or modification of it and will procure a written waiver in equivalent terms from its employees, its sub-contractors and its sub-contractors’ employees.

- PROHIBITED MATERIALS

  - Subject to clause 3, the Contractor warrants to the Beneficiary that it will comply in all respects with its obligations contained in the Contract regarding Prohibited Materials.

  - Clause 5 does not create any additional duty for the Contractor to inspect or check the work of others which is not required by the Contract.

- PROFESSIONAL INDEMNITY INSURANCE

  - The Contractor confirms that it has taken out and will maintain Professional Indemnity Insurance, for the duration of the Liability Period with reputable insurers authorised to carry on business in the United Kingdom.

  - If such insurance is not available to the Contractor at commercially reasonable rates and terms (excluding any increase in premiums attributable to the actions, omissions, errors or defaults of the Contractor), the parties will meet, the Contractor will outline the steps it intends to take to manage such risks and the parties will use reasonable endeavours to agree a method of managing such risks.

  - The Contractor will provide the Beneficiary with a current broker’s letter confirming that the policies referred to in clause 6 are in full force and effect.

- NO APPROVAL

- The Contractor’s liabilities under this Deed will not in any way be reduced or extinguished by reason of any inspection or approval of any documents prepared by or on behalf of the Contractor or attendance at site meetings or other enquiry or inspection which the Beneficiary may make or procure to be made for the Beneficiary’s benefit or on its behalf.

- ASSIGNMENT

- The Beneficiary may, without the consent of the Contractor [and without prejudice to the provisions of clause 15], assign any of its rights under this Deed to any person by way of absolute legal assignment, on not more than two occasions only. Any assignment (whether by legal assignment, equitable assignment, charge or otherwise and including re-assignments) to and from any Associate of the Beneficiary or any party providing finance to the Beneficiary (or any Associate of the Beneficiary) will not count towards the number of assignments permitted without consent under clause 8. The Beneficiary will notify the Contractor of any assignment specifying the name and address of the assignee and the date of the assignment. The Contractor will not contend that any such assignee is precluded from recovering any loss resulting from any breach of this Deed (whatever the date of such breach) by reason only that that person is an assignee and not the original beneficiary under this Deed or by reason that the original beneficiary or any intermediate beneficiary escaped any loss resulting from such breach by reason of the disposal of any interest in the Site or that the original beneficiary or any intermediate beneficiary has not suffered any or as much loss.

- FURTHER WARRANTIES

  - The Contractor will within 14 days of a request made at any time by the Beneficiary, duly execute and deliver as a deed a collateral warranty in the same terms as this Deed with due alteration of detail (save for clause 9 [and clause 15]) in favour of:

    - any purchaser acquiring the whole or any part of the Beneficiary’s Interest in the Project and/or the Site;

    - any tenant acquiring a leasehold interest in the whole or any part of the Project and/or the Site;

    - any funder providing finance in connection with the whole or any part of the Project and/or the Site,

- provided that the Contractor has not already executed a collateral warranty in favour of that purchaser, tenant or funder (as the case may be).

- NOTICES

  - Any notice or other communication given under or in connection with this Deed must be in writing and sent by first class post, delivered to or left at the recipient’s registered office or, if there is none, its last known address.

  - Any notice given complying with clause 10.1 will be deemed to be served if given by first class post at 9.00am on the next working day after the date of posting, or if delivered or left at the correct address, on the date of delivery.

- OTHER RIGHTS AND REMEDIES

- The rights and benefits conferred upon the Beneficiary by this Deed are in addition to any other rights and remedies it may have against the Contractor including, without limitation, any remedies in negligence.

- LIMITATION

  - The Contractor has no liability under this Deed which is greater or of longer duration than it would have had if, instead of this Deed, the Beneficiary had been a party to the Contract as joint employer, provided that the Contractor will not be entitled to set-off or deduct from any sums payable to the Beneficiary under this Deed any sums due or claimed as due by the Contractor from the Employer.

  - The Contractor will be entitled in any action or proceedings brought by the Beneficiary under this Deed to rely on any limitation in the Contract and to raise equivalent rights in defence of liability (but excluding set-offs and counterclaims) as it would have against the Beneficiary if, instead of this Deed, the Beneficiary had been a party to the Contract as joint employer.

  - No action or proceedings may be brought or commenced under this Deed at any time after the Liability Period provided that:

any action under statute may be brought or commenced within any longer prescribed statutory limitation period;

any such action or proceedings for breach of this Deed which relate to a Building Safety Liability may be brought or commenced before the expiry of the limitation period which applies to the Building Safety Liability or the Civil Liability (Contribution) Act 1978; and

the parties shall not plead in defence of any action or proceedings referred to in clauses 12.3.1 and 12.3.2 any shorter limitation period whether under the Limitation Act 1980 or otherwise.

- THIRD PARTY RIGHTS

- The parties do not intend that any term of this Deed will be enforceable by any person under the Contracts (Rights of Third Parties) Act 1999, except that any Associate of the Beneficiary may in their own right enforce a term of this Deed.

- GOVERNING LAW AND JURISDICTION

  - This Deed and any non-contractual obligations arising out of or in connection with it will be governed by English Law.

  - The courts of England and Wales have exclusive jurisdiction to determine any dispute arising out of or in connection with this Deed (including, without limitation, in relation to any non-contractual obligations). The parties irrevocably submit to the jurisdiction of those courts.

- [STEP-IN RIGHTS

  - Subject to clause 15.8, the Contractor will not exercise or seek to exercise any Termination Right, without first giving the Beneficiary a notice which:

    - is served not less than the Notice Period before the exercise of the Termination Right;

    - states the Contractor’s intention to exercise the Termination Right; and

    - specifies the Contractor’s grounds for exercising the Termination Right and states the amount (if any) of monies outstanding under the Contract.

  - Within the Notice Period the Beneficiary may give notice to the Contractor expressly confirming its intention to comply with clause 15.3.2 and that the Beneficiary will become the employer under the Contract to the exclusion of the Employer and, upon giving such notice, that will be the case and the Contract will be and remain in full force and effect notwithstanding any of the grounds in the Contractor’s notice under clause 15.1.

  - If the Beneficiary has given notice under clause 15.2 or under clause 15.5, the Beneficiary will:

    - as soon as practicable remedy any outstanding breach by the Employer; and

    - from the date of the Contractor’s notice (if the Beneficiary has given notice under clause 15.2) or the date of the Beneficiary’s notice (if the Beneficiary has given notice under clause 15.5), become responsible for all sums properly payable to the Contractor under the Contract and for the observance and performance of all of the other duties and obligations on the part of the Employer to be observed and performed under the Contract accruing due after the service of the Contractor’s notice or Beneficiary’s notice (as applicable). The Beneficiary will, in paying such sums, be entitled to the same rights of set-off and deduction as would have applied to the Employer under the Contract.

  - Notwithstanding anything contained in this Deed and notwithstanding any payments which may be made by the Beneficiary to the Contractor the Beneficiary will not be under any obligation to the Contractor nor will the Contractor have any claim or cause of action against the Beneficiary unless and until the Beneficiary has given notice to the Contractor under either clause 15.2 or clause 15.5.

  - If requested by the Beneficiary by notice expressly confirming the Beneficiary’s intention to comply with clause 15.3.2 and subject to clause 15.3.1 and clause 15.3.2, the Contractor agrees to accept the instructions of the Beneficiary to the exclusion of the Employer in respect of the Project upon the terms and conditions of the Contract. The Beneficiary will then become the employer under the Contract to the exclusion of the Employer and the Contractor will, if so requested, enter into a novation agreement to confirm the substitution of the Beneficiary for the Employer under the Contract.

  - The Employer acknowledges that the Contractor will be entitled to rely on a notice given to the Contractor by the Beneficiary under clause 15.5 as conclusive evidence that the Beneficiary is entitled to serve such notice.

  - The Beneficiary may by notice to the Contractor appoint another person to exercise its rights under clause 15 subject to the Beneficiary remaining liable to the Contractor as guarantor for its appointee in respect of its obligations under this Deed.

  - Where the Contractor is seeking to exercise a right to suspend the performance of any duties or obligations under the Contract as a result of non-payment or in accordance with s112 of the Housing Grants, Construction and Regeneration Act 1996, the Contractor will give to the Beneficiary notice of its intention so to do at the same time as it serves notice on the Employer.

  - Notwithstanding the other provisions of clause 15, if the Contract has for any reason been terminated prior to Contractor’s receipt of the Beneficiary’s notice under clause 15.2 or clause 15.5, the Contractor will on receipt of the Beneficiary’s notice enter into a new contract with the Beneficiary on the same terms as the Contract to continue the services in all respects as if the Contract had been transferred to the Beneficiary in accordance with the provisions of clause 15.

  - [Where the Contractor has given rights in relation to the Contract similar to those contained in clause 15 to any other person then if both the Beneficiary and such other person serve notice under clause 15.2 or clause 15.5 or its equivalent the notice served by the Beneficiary will [prevail] [not prevail][not prevail over any notice given by [NAME] but prevail over any notice served by any other party.]]

- COUNTERPARTS

- This Deed may be executed in any number of counterparts, each of which will constitute an original, but which will together constitute one agreement.

- THIS DOCUMENT is executed as a deed and delivered on the date stated in the Particulars.

- [ALL PARTIES TO EXECUTE]

# PART 5A: THIRD PARTY RIGHTS

- INTERPRETATION

## Expressions defined in the Contract shall have the same meanings for the purposes of the Third Party Rights set out in this Part 5A of Schedule 7.

- CONTRACTOR’S WARRANTIES

- The Contractor warrants to the Third Party that it has performed and shall continue to perform its duties under the Contract in accordance with the Contract and that it has exercised and shall continue to exercise reasonable skill and care in relation to (so far as the Contractor is responsible for them):

  - the design of the Works;

  - the selection of goods, materials, equipment or plant for the Works; and

  - the satisfaction of any performance requirement or specification of or for the Works.

- INTELLECTUAL PROPERTY RIGHTS

  - All Intellectual Property in the Contractor’s Design Documents shall remain vested in the Contractor.

  - The Contractor grants to the Third Party, with immediate effect an irrevocable, royalty-free, non-exclusive licence

Such licence will:

    - remain in full force and effect notwithstanding the completion of the Contractor’s obligations or the termination of the Contract or the determination of the Contractor’s engagement under the Contract or any dispute under the Contract;

    - allow the Third Party to use the Intellectual Property and to reproduce all Contractor’s Design Documents for any purpose whatsoever connected with the Works including, but without limitation, the execution, completion, maintenance, letting, advertisement, modification, reinstatement and repair of the Works;

    - carry the right to grant sub-licences and will be transferable to third parties; and

    - enable the Third Party to use and reproduce the Contractor’s Design Documents for any extension of the Works, but not include a licence to reproduce the Intellectual Property in the Contractor’s Design Documents for any extension of the Works.

  - The Contractor shall not grant to any third party the right to use any of the Contractor’s Design Documents or any Intellectual Property in any of the Contractor’s Design Documents except under any warranty or as a result of any Third Party Rights it is obliged to give under the Contract.

  - The Contractor shall have no liability for any use by the Third Party of any of the Contractor’s Design Documents for any purpose other than that for which they were prepared.

  - The Contractor warrants that the Contractor’s Design Documents (save to the extent that duly authorised sub-contractors or sub-consultants are used) are the Contractor’s own original work and that in any event their use in connection with the Works shall not infringe the rights of any third party. The Contractor further warrants that where duly authorised sub-contractors or sub-consultants are used their work shall be original and shall be covered by the licence granted under paragraph 3.2.

  - The Contractor will:

keep electronic copies of the Contractor’s Design Documents and any other documents required to be prepared or obtained by the Contractor under the Contract in a readable form for a period of 15 years from practical completion of the Works; and

on reasonable request at any time and following reasonable prior written notice to give to the Third Party, or those authorised by the Third Party, access to such documents and to provide copies (including electronic and digital copies in a readable form) of such documents at the expense of the Third Party as the case may be.

- PROHIBITED MATERIALS

  - The Contractor warrants to the Third Party that it shall comply in all respects with its obligations contained in clause 2.2.6 of the Contract regarding Prohibited Materials.

  - This paragraph 4 does not create any additional duty for the Contractor to inspect or check the work of others which is not required by the Contract.

- PROFESSIONAL INDEMNITY INSURANCE

  - The Contractor shall at its own cost maintain professional indemnity insurance with reputable insurers authorised to carry on business in United Kingdom with limits of indemnity of the types and amounts not less than those stated in the Contract Particulars until the expiry of the period stated in the Contract Particulars from the date of practical completion of the Works, on terms that do not require the Contractor to discharge any liability before being entitled to recover from the insurers and that would not adversely affect the rights of any person to recover from the insurers under the Third Parties (Rights Against Insurers) Act 2010 and provided the insurance is available at commercially reasonable rates.

  - Any increased or additional premium required by insurers due to the Contractor’s own claims record or other acts, omissions, matters or things particular to the Contractor shall be treated as within commercially reasonable rates.

  - The Contractor, as and when reasonably requested to do so, shall produce to the Third Party for inspection documentary evidence (by way of insurer’s or broker’s letter) that such insurance has been effected and is being maintained and renewed annually.

- NO APPROVAL

## The Contractor’s liabilities under Part 5A of Schedule 7 shall not be in any way reduced or extinguished by reason of any inspection or approval of the Contractor’s Design Documents or attendance at site meetings or other enquiry or inspection which the Third Party may make or procure to be made for the Third Party’s benefit or on its behalf.

- ASSIGNMENT

## Without prejudice to the provisions of paragraph 12, the rights on the part of the Third Party under Part 5A of Schedule 7 may be assigned to any person by way of absolute legal assignment, without the consent of the Contractor on two occasions only. An assignment by the Third Party to and from any Associate of the Third Party, or an assignment (whether by legal assignment, equitable assignment, charge or otherwise and including re-assignments) to and from any party providing finance to the Third Party (or any Associate of the Third Party) shall not count towards the number of assignments permitted without consent under paragraph 7. The Third Party shall give the Contractor written notice following any such assignment specifying the name and address of the assignee and the date of the assignment. The Contractor shall not contend that any such assignee is precluded from recovering any loss resulting from any breach of Part 5A of Schedule 7 (whatever the date of such breach) by reason only that that person is an assignee and not the original Third Party under Part 5A of Schedule 7 or by reason that the original Third Party or any intermediate Third Party escaped any loss resulting from such breach by reason of the disposal of any interest in the site of the Works or that the original Third Party or any intermediate Third Party has not suffered any or as much loss.

- NOTICES

  - Any notice or other communication given by the Contractor or the Third Party under Part 5A of Schedule 7 must be in writing and sent by first class post, delivered to or left at the recipient’s registered office or, if there is none, its last known address.

  - Any notice given complying with paragraph 8.1 will be deemed to be served, if given by first class post at 9.00am on the next working day after the date of posting, or if delivered or left at the correct address, on the date of delivery.

- OTHER RIGHTS AND REMEDIES

## The rights and benefits conferred upon the Third Party by Part 5A of Schedule 7 are in addition to any other rights and remedies it may have against the Contractor including, without limitation, any remedies in negligence.

- LIMITATION

  - The Contractor has no liability under Part 5A of Schedule 7 which is greater or of longer duration than it would have had if, in lieu of Part 5A of Schedule 7, the Third Party had been a party to the Contract as joint employer, provided that the Contractor shall not be entitled to set-off or deduct from any sums payable to the Third Party any sums due or claimed as due by the Contractor from the Employer.

  - The Contractor shall be entitled in any action or proceedings brought by the Third Party under Part 5A of Schedule 7 to rely on any limitation in the Contract and to raise equivalent rights in defence of liability (but excluding set-offs and counterclaims) as it would have against the Third Party if, in lieu of Part 5A of Schedule 7, the Third Party had been a party to the Contract as joint employer.

  - No action or proceedings may be brought or commenced under Part 5A of Schedule 7 at any time after the date being 12 years after the date of practical completion of the Works provided that:

any action under statute may be brought or commenced within any longer prescribed statutory limitation period;

any such action or proceedings for breach of Part 5A of Schedule 7 which relate to a Building Safety Liability may be brought or commenced before the expiry of the limitation period which applies to the Building Safety Liability or the Civil Liability (Contribution) Act 1978; and

the parties shall not plead in defence of any action or proceedings referred to in paragraphs 10.3.1 and 10.3.2 any shorter limitation period whether under the Limitation Act 1980 or otherwise.

  - The Contractor shall not by reason of Part 5A of Schedule 7 have any liability to the Third Party for delay in completion of the Works or any part of them.

  - The Third Party has no authority to issue any direction or instruction to the Contractor in relation to the Contract.

- GOVERNING LAW AND JURISDICTION

  - This Part 5A of Schedule 7 shall be governed by English Law.

  - The Contractor and the Third Party agree that the courts of England and Wales shall have exclusive jurisdiction to determine any dispute arising out of or in connection with Part 5A of Schedule 7 (including in relation to any non-contractual obligations). The Contractor and the Third Party irrevocably submit to the jurisdiction of those courts.

- STEP-IN RIGHTS

- Where the Third Party is a Purchaser or Funder of the whole or a substantial part of the Works:

  - Subject to paragraph 12.6 of Part 5A of Schedule 7, the Contractor shall not exercise or seek to exercise any right which may be or become available to it to terminate or treat as terminated or repudiated the Contract or its employment under it or discontinue or suspend the performance of any duties or obligations under the Contract, without first giving to the Third Party not less than twenty-eight days’ prior written notice specifying the Contractor’s grounds for terminating or treating as terminated or repudiated the Contract or its employment under it or discontinuing or suspending its performance of the Contract and stating the amount (if any) of monies outstanding under the Contract. Within that 28-day period:

    - the Third Party may give written notice to the Contractor in the form at Part 5B of Schedule 7 expressly confirming its intention to comply with paragraph 12.1.2 and 12.1.3 and that the Third Party shall become the employer under the Contract to the exclusion of the Employer and, upon giving such notice, that shall be the case and the Contract shall be and remain in full force and effect notwithstanding any of the grounds in the Contractor’s notice under paragraph 12.1; and

    - if the Third Party has given notice under paragraph 12.1.1 or under paragraph 12.3, the Third Party shall then as soon as practicable remedy any outstanding breach by the Employer; and

    - if:

      - the Third Party has given notice under paragraph 12.1.1 then from the date of receipt by the Third Party of the Contractor’s notice; or

      - the Third Party has given notice under paragraph 12.3 then from the date of receipt by the Contractor of the Third Party’s notice,

- the Third Party shall, by virtue of the Third Party’s notice, become responsible for all sums properly payable to the Contractor under the Contract and for the observance and performance of all of the other duties and obligations on the part of the Employer to be observed and performed under the Contract accruing due after the service of such Contractor’s notice or Third Party’s notice (as applicable) but the Third Party shall in paying sums be entitled to the same rights of set-off and deduction as would have applied to the Employer under the Contract.

  - Notwithstanding anything contained in Part 5A of Schedule 7 and notwithstanding any payments which may be made by the Third Party to the Contractor, the Third Party shall not be under any obligation to the Contractor nor shall the Contractor have any claim or cause of action against the Third Party unless and until the Third Party has given written notice to the Contractor under either paragraph 12.1.1 or paragraph 12.3.

  - The Contractor further covenants with the Third Party that if requested by the Third Party by written notice in the form at Part 5B of Schedule 7 expressly confirming the Third Party’s intention to comply with paragraph 12.1.3 and subject to paragraph 12.1.2 and paragraph 12.1.3, it shall accept the instructions of the Third Party to the exclusion of the Employer in respect of the Works upon the terms and conditions of the Contract. The Third Party shall then become the employer under the Contract to the exclusion of the Employer and the Contractor shall, if so requested, enter into a novation agreement as a deed in order to substitute the Third Party for the Employer under the Contract.

  - Where the Contractor has given rights in relation to the Contract similar to those contained in this paragraph 12 to any other person then if both the Third Party and any such other person serve notice under paragraph 12.1.1 or paragraph 12.3 or its equivalent the notice served first shall prevail.

  - The Employer acknowledges that the Contractor shall be entitled to rely on a notice given to the Contractor by the Third Party under paragraph 12.3 as conclusive evidence that the Third Party is entitled to serve such notice.

  - Where the Contractor is seeking to exercise a right to suspend the performance of any duties or obligations under the Contract as a result of non-payment or in accordance with s112 of the Housing Grants, Construction and Regeneration Act 1996, the Contractor shall give to the Third Party written notice of its intention so to do at the same time as it serves notice on the Employer.

  - The Third Party may by written notice to the Contractor appoint another person to exercise its rights under this paragraph 12 subject to the Third Party remaining liable to the Contractor as guarantor for its appointee in respect of its obligations under Part 5A of Schedule 7 and as set out in the written notice served under paragraph 12.1.1 or 12.3.

  - Notwithstanding the other provisions of paragraph 12, if the Contract has for any reason been terminated prior to receipt by the Contractor of a notice from the Third Party served under paragraph 12.1.1 or paragraph 12.1.3, the Contractor shall on receipt of any such notice from the Third Party enter into a new contract with the Beneficiary on the same terms as the Contract to continue the services in all respects as if the Contract had been transferred to the Third Party in accordance with the provisions of paragraph 12.

- SCHEDULE 7

- Part 5B: Step-In Notice

[NAME AND ADDRESS OF CONTRACTOR]

- [DATE]

- Dear [NAME]

- step-in notice

We refer to the Building Contract dated [DATE](“the Contract”) between you and [NAME OF EMPLOYER] (“the Employer”). Words and expressions defined in the Contract shall have the same meanings in this letter.

- In accordance with Part 5A of Schedule 7 paragraph 12.1.1 of the Contract, we give you written notice confirming our intention to comply with Part 5A of Schedule 7 paragraph 12.1.2 and 12.1.3 of the Contract and that we shall become the employer under the Contract to the exclusion of the Employer.

- In consideration of you complying with Part 5A of Schedule 7 of the Contract we agree to the following:

- We shall as soon as practicable remedy any outstanding breach by the Employer in accordance with Part 5A of Schedule 7; and

- With effect from the date of receipt by you of this notice, or the date of receipt by us of your notice served under Part 5A of Schedule 7 of the Contract (as applicable), we shall be responsible for all sums properly payable to you under the Contract and for the observance and performance of all of the other duties and obligations on the part of the Employer to be observed and performed under the Contract accruing due after the service of this notice, or your notice served under Part 5A of Schedule 7 of the Contract (as applicable) provided always that in paying such sums you acknowledge that we shall be entitled to the same rights of set-off and deduction as would have applied to the Employer under the Contract.

Yours faithfully

______________________________

For and on behalf of [NAME]

# SCHEDULE 7

# Part 5C: Nominating Notice

# TO:	[NAME] (company registration number [NUMBER]) whose registered office is at [ADDRESS]

FROM: [NAME] (company registration number [NUMBER]) whose registered office is at [ADDRESS] (“the Employer”)]

Dear [NAME]

Date:	[DATE]

# [DETAILS OF WORKS] (“the Works”)

# You have entered into a contract with the Employer dated [DATE] in respect of the Works (“the Contract”).

# Part 5A of Schedule 7 of the Contract sets out the benefits and rights which may be enforced by a third party on the issue of this notice. On behalf of the Employer we nominate [NAME] (Company registration number [NUMBER]) as a third party (“the Third Party”) entitled to enforce the benefits and rights set out in Part 5A of Schedule 7 of the Contract in accordance with the terms of the Contract as from the date of this notice.

# [The Third Party has taken or agreed to take a lease of the premises known as [DESCRIBE] forming part of the Works] [The Third Party has agreed to purchase the whole [or part] of the property of which the Works forms part] The Third Party has provided finance in connection with the [purchase][lease] of [the Site][DESCRIBE PART OF THE SITE] [The Third Party has [DESCRIBE INTEREST].

# Yours faithfully

______________________________

For and on behalf of [EMPLOYER]

SCHEDULE 7

PART 6: CONTRACTOR’S DESIGN TEAM’S COLLATERAL WARRANTY

| - Dated: 2026 - [CONSULTANT] - [BENEFICIARY] - [CONTRACTOR] |  |
| --- | --- |
| [SPECIFY DISCIPLINE OF CONSULTANT] Consultant Warranty |
| relating to [SPECIFY] |

PARTICULARS

| Date of this Deed |  |
| --- | --- |
| Consultant | [NAME][(registered number [NUMBER] [whose registered office is at] [of] [ADDRESS]. |
| Beneficiary | [NAME][(registered number [NUMBER] [whose registered office is at] [of] [ADDRESS]. |
| Client | [NAME][(registered number [NUMBER] [whose registered office is at] [of] [ADDRESS]. |
| Appointment | the appointment dated [DATE] made between the Consultant and the Client. |
| Beneficiary’s Interest | The Beneficiary is [providing finance in connection with the Project, whether that person acts on its own account, as agent for a syndicate of other parties or otherwise] [the/a] [landlord][freehold owner] [purchaser] [tenant] of [the Site] [DESCRIPTION OF PART OF THE SITE]. |
| [Documents | all drawings, designs, charts, specifications, plans and any other documents or materials (including any computer software developed by the Consultant used to generate them and any designs contained in them) but excluding internal memoranda and documents, working papers and templates, which have been created and/or developed by the Consultant in the course of performing its obligations under the Appointment.] |
| Liability Period | the period from the date of this Agreement until the date 12 years after the later of the date of completion of the Services or the date of practical completion of the Project. |
| [Notice Period | [28] days.] |
| Project | the [DESCRIBE PROJECT] at the Site. |
| Professional Indemnity Insurance | professional indemnity insurance with a minimum limit of indemnity of not less than £[FIGURES]([WORDS] million pounds) for any one occurrence or series of occurrences arising out of any one event. |
| Services | the services to be provided by the Consultant set out in the Appointment. |
| Site | [DETAILS]. |
| Termination Right | a right which may be or become available to the Consultant to terminate or treat as terminated or repudiated the Appointment or its engagement under it or discontinue or suspend the performance of any duties or obligations under the Appointment. |
| Third Parties | - a) any company, bank or institution providing finance in connection with or secured (whether by charge, sale and leaseback or otherwise) upon the Project - b) any purchaser of the Project or any part of it or c) any tenant of the Project or any part of it. |

THIS DEED is made on the date set out in the Particulars

- BETWEEN:

- the Consultant;[and]

- the Beneficiary[; and

- the Client]. [To be included where clause 15 (Step-in Rights) applies]

- BACKGROUND:

- The Client has appointed the Consultant under the Appointment to provide the Services in relation to the Project.

- The Beneficiary’s Interest in the Project is set out in the Particulars.

- The Consultant is obliged under the Appointment to give a warranty in this form in favour of the Beneficiary.

- OPERATIVE PROVISIONS

- DEFINITIONS

- Subject to the words defined in the Particulars (which will have that meaning throughout this Deed), the words defined in the Appointment will have the same meaning in this Deed.

- CONSIDERATION

- This Deed is made in consideration of the payment of one pound (£1.00) by the Beneficiary to the Consultant receipt of which the Consultant acknowledges.

- CONSULTANT’S DUTIES UNDER THE APPOINTMENT

- The Consultant warrants to the Beneficiary that it has performed and will continue to perform its obligations under the Appointment in accordance with the Appointment and that it has exercised and will continue to exercise the reasonable skill and care to be expected of a properly qualified member and competent person in the Consultant’s Profession experienced in carrying out work such as the Services in relation to developments of similar scope, size, nature, timescale and complexity as the Project.

- INTELLECTUAL PROPERTY RIGHTS

  - Subject to the following provisions of this Deed, all Intellectual Property in the Documents will remain vested in the Consultant.

  - The Consultant grants (or, if such a grant cannot legally take place until a later date, agrees to grant) to the Beneficiary with effect from the date of this Deed or in the case of any of the Intellectual Property not yet in existence with effect from its creation, an irrevocable, royalty-free, non-exclusive licence.

  - Such licence will:

    - remain in full force and effect notwithstanding the completion of the Consultant’s obligations or the termination of the Appointment or this Deed or the determination of the Consultant’s engagement under the Appointment or any dispute under the Appointment or this Deed;

    - allow the Beneficiary to use the Intellectual Property and to reproduce all Documents for any purpose whatsoever connected with the Project including, but without limitation, the execution, completion, maintenance, letting, advertisement, modification, reinstatement and repair of the Project;

    - carry the right to grant sub-licences and will be transferable to third parties; and

    - enable the Beneficiary to use and reproduce the Documents for any extension of the Project, but not include a licence to reproduce the Intellectual Property in the Documents for any extension of the Project.

  - The Consultant will not grant to any third party the right to use any of the Documents except under any warranty or third party rights it is obliged to give under the Appointment or under this Deed or as otherwise required to enable it to fulfil its obligations under the Appointment.

  - The Consultant will not be liable for any use the Beneficiary may make of the Documents for any purpose other than that for which they were prepared.

  - The Consultant warrants that the Documents (except to the extent that duly authorised sub-consultants have been used to prepare the same) are the Consultant’s own original work and that in any event their use in connection with the Project will not infringe the rights of any third party. The Consultant further warrants that where duly authorised sub-consultants are used their work will be original and that their work will be covered by the licence granted to the Beneficiary under clause 4.2.

  - The Consultant will:

keep electronic copies of the Documents in a readable form for a period of 15 years from practical completion of the Works; and

on reasonable request at any time and following reasonable prior notice to give to the Beneficiary, or anyone authorised by the Beneficiary, access to the Documents and to provide copies (including electronic copies in a readable form) of the Documents at the Beneficiary’s expense.

  - The Consultant waives any moral rights in the Documents or in relation to the Project that it may have under Part 1 Chapter IV of the Copyright, Designs and Patents Act 1988 or any re-enactment or modification of it and will procure a written waiver in equivalent terms from its employees, its sub-consultants and its sub-consultants’ employees.

- PROHIBITED MATERIALS

  - Subject to clause 3, the Consultant warrants to the Beneficiary that it will comply in all respects with its obligations set out in the Appointment regarding Prohibited Materials.

  - Clause 5.1 does not create any additional duty for the Consultant to inspect or check the work of others which is not required by the Appointment.

- PROFESSIONAL INDEMNITY INSURANCE

  - The Consultant confirms that it has taken out and will maintain Professional Indemnity Insurance, for the duration of the Liability Period with reputable insurers authorised to carry on business in the United Kingdom.

  - If such insurance is not available to the Consultant at commercially reasonable rates and terms (excluding any increase in premiums attributable to the actions, omissions, errors or defaults of the Consultant), the parties will meet, the Consultant will outline the steps it intends to take to manage such risks and the parties will use reasonable endeavours to agree a method of managing such risks.

  - The Consultant will provide the Beneficiary with a current broker’s letter confirming that the policies referred to in clause 6 are in full force and effect.

- NO APPROVAL

- The Consultant’s liabilities under this Deed will not in any way be reduced or extinguished by reason of any inspection or approval of the Documents or attendance at site meetings or other enquiry or inspection which the Beneficiary may make or procure to be made for the Beneficiary’s benefit or on its behalf.

- ASSIGNMENT

- The Beneficiary may, without the consent of the Consultant [and without prejudice to the provisions of clause 15] [Delete if Clause 15 (Step-in Rights) does not apply], assign any of its rights under this Deed to any person by way of absolute legal assignment, on not more than two occasions only. Any assignment (whether by legal assignment, equitable assignment, charge or otherwise and including re-assignments) to and from any Associate of the Beneficiary or any party providing finance to the Beneficiary (or any Associate of the Beneficiary) will not count towards the number of assignments permitted without consent under clause 8. The Beneficiary will notify the Consultant of any assignment specifying the name and address of the assignee and the date of the assignment. The Consultant will not contend that any such assignee is precluded from recovering any loss resulting from any breach of this Deed (whatever the date of such breach) by reason only that that person is an assignee and not the original beneficiary under this Deed or by reason that the original beneficiary or any intermediate beneficiary escaped any loss resulting from such breach by reason of the disposal of any interest in the Site or that the original beneficiary or any intermediate beneficiary has not suffered any or as much loss.

- FURTHER WARRANTIES

## The Consultant will within 14 days of a request made at any time by the Beneficiary, duly execute and deliver as a deed a collateral warranty in the same terms as this Deed with due alteration of detail (save for clause 9 [and clause 15] [Delete if Clause 15 (Step-in Rights) does not apply]) in favour of each Third Party provided that the Consultant has not already executed a collateral warranty in favour of that Third Party.

- NOTICES

  - Any notice or other communication given under or in connection with this Deed must be in writing and sent by first class post, delivered to or left at the recipient’s registered office or, if there is none, its last known address.

  - Any notice given complying with clause 10.1 will be deemed served if given by first class post at 9.00am on the next working day after the date of posting, or if delivered or left at the correct address, on the date of delivery.

- OTHER RIGHTS AND REMEDIES

- The rights and benefits conferred upon the Beneficiary by this Deed are in addition to any other rights and remedies it may have against the Consultant including, without limitation, any remedies in negligence.

- LIMITATION

  - The Consultant has no liability under this Deed which is greater or of longer duration than it would have had if, instead of this Deed, the Beneficiary had been a party to the Appointment as joint employer, provided that the Consultant will not be entitled to set-off or deduct from any sums payable to the Beneficiary under this Deed any sums due or claimed as due by the Consultant from the Client.

  - The Consultant will be entitled in any action or proceedings brought by the Beneficiary under this Deed to rely on any limitation in the Appointment and to raise equivalent rights in defence of liability (but excluding set-offs and counterclaims) as it would have against the Beneficiary if, instead of this Deed, the Beneficiary had been a party to the Appointment as joint employer.

  - No action or proceedings may be brought or commenced under this Deed at any time after the Liability Period provided that:

any action under statute may be brought or commenced within any longer prescribed statutory limitation period;

any such action or proceedings for breach of this Deed which relate to a Building Safety Liability may be brought or commenced before the expiry of the limitation period which applies to the Building Safety Liability or the Civil Liability (Contribution) Act 1978; and

the parties shall not plead in defence of any action or proceedings referred to in clauses 12.3.1 and 12.3.2 any shorter limitation period whether under the Limitation Act 1980 or otherwise.

- THIRD PARTY RIGHTS

- [Use where the warranty is being provided by a Consultant employed by the Client]

- [The Parties do not intend that any term of this Deed will be enforceable by any person under the Contracts (Rights of Third Parties) Act 1999, except that any Associate of the Beneficiary may in its own right enforce a term of this Deed.]

[Use where the warranty is being provided by a Sub-Consultant in favour of the Employer]

  - Subject to clause 13.2, the parties do not intend that any term of this Deed will be enforceable by any person under the Contracts (Rights of Third Parties) Act 1999, except that any Associate of the Beneficiary may in its own right enforce a term of this Deed.

  - The Beneficiary and the Sub-Consultant agree that, notwithstanding any other provision of this Deed, unless the Sub-Consultant has already provided a collateral warranty to the relevant Third Party in accordance with the terms of the Appointment or this Deed, the rights set out in this Deed will vest in the Third Parties on the date on which the Beneficiary issues a notice to that effect to the Sub-Consultant, stating the name of the relevant Third Party, the nature of its interest in the Project and the relevant clauses of this Deed that will apply.

  - Subject to clause 13.4, the Beneficiary and the Sub-Consultant will be entitled to:

    - agree any waiver or release under or arising from or in respect of this Deed; and

    - agree to settle any dispute or other matter arising out of or in connection with this Deed,

### in each case in or on such terms as they, in their absolute discretion, think fit, without the consent of any of the Third Parties.

  - After the rights have vested in a Third Party in accordance with clause 13.2 the Beneficiary and the Sub-Consultant will not be entitled to amend or vary the express provisions of this Deed without the consent of the relevant Third Party.]

- GOVERNING LAW AND JURISDICTION

  - This Deed and any non-contractual obligations arising out of or in connection with it will be governed by English Law.

  - The courts of England and Wales have exclusive jurisdiction to determine any dispute arising out of or in connection with this Deed (including (without limitation) in relation to any non-contractual obligations). The parties irrevocably submit to the jurisdiction of those courts.

- [STEP-IN RIGHTS [Delete if Step-in Rights do not apply]

  - Subject to clause 15.8, the Consultant will not exercise or seek to exercise any Termination Right without first giving to the Beneficiary a notice which:

    - is served not less than the Notice Period before the exercise of the Termination Right;

    - states the Consultant’s intention to exercise the Termination Right; and

    - specifies the Consultant’s grounds for exercising the Termination Right and states the amount (if any) of monies outstanding under the Appointment.

  - Within the Notice Period the Beneficiary may give notice to the Consultant expressly confirming its intention to comply with clause 15.3.2 and that the Beneficiary will become the client under the Appointment to the exclusion of the Client and, upon giving such notice, that will be the case and the Appointment will be and remain in full force and effect notwithstanding any of the grounds in the Consultant’s notice under clause 15.1.

  - If the Beneficiary has given notice under clause 15.2 or under clause 15.5, the Beneficiary will:

    - as soon as practicable remedy any outstanding breach by the Client; and

    - from the date of the Consultant’s notice (if the Beneficiary has given notice under clause 15.2 or the date of the Beneficiary’s notice (if the Beneficiary has given notice under clause 15.5) become responsible for all sums properly payable to the Consultant under the Appointment and for the observance and performance of all of the other duties and obligations on the part of the Client to be observed and performed under the Appointment accruing due after the service of such Consultant’s notice or Beneficiary’s notice (as applicable). The Beneficiary will, in paying such sums, be entitled to the same rights of set-off and deduction as would have applied to the Client under the Appointment.

  - Notwithstanding anything contained in this Deed and notwithstanding any payments which may be made by the Beneficiary to the Consultant, the Beneficiary will not be under any obligation to the Consultant nor will the Consultant have any claim or cause of action against the Beneficiary unless and until the Beneficiary has given notice to the Consultant under either clause 15.2 or clause 15.5.

  - If requested by the Beneficiary by notice expressly confirming the Beneficiary’s intention to comply with clause 15.3.2 and subject to clause 15.3.1 and clause 15.3.2, the Consultant agrees to accept the instructions of the Beneficiary to the exclusion of the Client in respect of the Project upon the terms and conditions of the Appointment. The Beneficiary will then become the client under the Appointment to the exclusion of the Client and the Consultant will, if so requested, enter into a novation agreement to confirm the substitution of the Beneficiary for the Client under the Appointment.

  - The Client acknowledges that the Consultant will be entitled to rely on a notice given to the Consultant by the Beneficiary under clause 15.5 as conclusive evidence that the Beneficiary is entitled to serve such notice.

  - The Beneficiary may by notice to the Consultant appoint another person to exercise its rights under clause 15 subject to the Beneficiary remaining liable to the Consultant as guarantor for its appointee in respect of its obligations under this Deed.

  - Where the Consultant is seeking to exercise a right to suspend the performance of any duties or obligations under the Appointment as a result of non-payment or in accordance with s112 of the Housing Grants, Construction and Regeneration Act 1996, the Consultant will give to the Beneficiary notice of its intention so to do at the same time as it serves notice on the Client.

  - Notwithstanding the other provisions of clause 15, if the Appointment has for any reason been terminated prior to receipt by the Consultant of the Beneficiary’s notice under clause 15.2 or clause 15.5, the Consultant will on receipt of the Beneficiary’s notice enter into a new appointment with the Beneficiary on the same terms as the Appointment to continue the Services in all respects as if the Appointment had been transferred to the Beneficiary in accordance with the provisions of clause 15.

  - [Where the Consultant has given rights in relation to the Appointment similar to those contained in clause 15 to any other person then if both the Beneficiary and any such other person serve notice under clause 15.2 or clause 15.5 or its equivalent the notice served by the Beneficiary will [prevail] [not prevail] [not prevail over any notice served by [NAME][Name] but prevail over any notice served by any other person].]

- COUNTERPARTS

- This Deed may be executed in any number of counterparts, each of which will constitute an original, but which will together constitute one agreement.

THIS DOCUMENT is executed as a deed and delivered on the date stated in the Particulars.

[ALL PARTIES TO EXECUTE]

SCHEDULE 7

PART 7: SUB-CONTRACTOR’S COLLATERAL WARRANTY

| - Dated: 2026 - [SUB-CONTRACTOR] - [BENEFICIARY] - [CONTRACTOR] |  |
| --- | --- |
| Sub-Contractor warranty |
| relating to [SPECIFY] |

PARTICULARS

| Date of this Deed |  |
| --- | --- |
| Sub-Contractor | [NAME][(registered number [NUMBER] [whose registered office is at] [of] [ADDRESS]. |
| Beneficiary | [NAME][(registered number [NUMBER] [whose registered office is at] [of] [ADDRESS]. |
| Contractor | [NAME][(registered number [NUMBER] [whose registered office is at] [of] [ADDRESS]. |
| Beneficiary’s Interest | the Beneficiary is [the Employer under the Main Contract][providing finance in connection with the Project, whether that person acts on its own account, as agent for a syndicate of other parties or otherwise] [the/a] [landlord][freehold owner] [purchaser] [tenant] of [the Site] [DESCRIPTION OF PART OF THE SITE]. |
| Associates | “associated persons” and “associates”, as such terms are defined by sections 121 and 131 of the BSA. |
| BSA | the Building Safety Act 2022. |
| Building Safety Liability | any liability of the Sub-Contractor or the Beneficiary that arises as a result of the BSA and/or the Defective Premises Act 1972 and/or section 38 of the Building Act 1984 whether under the Civil Liability (Contribution) Act 1978 or otherwise. |
| Documents | all drawings, designs, charts, specifications, plans and any other documents or materials (including any computer software developed by the Sub-Contractor used to generate them and any designs contained in them) but excluding internal memoranda and documents, working papers and templates, which have been created and/or developed by the Sub-Contractor in the course of performing its obligations under the Sub-Contract. |
| [Employer | [NAME][(registered number [NUMBER] [whose registered office is at] [of] [ADDRESS].] [Delete if the Beneficiary is the Employer] |
| Insurance | [professional indemnity][product liability] insurance with a minimum limit of indemnity of not less than £[FIGURES] ([WORDS] million pounds) for any one occurrence or series of occurrences arising out of any one event. |
| Intellectual Property | all copyright and all neighbouring and database rights and moral rights, registered designs, registered and unregistered design rights, or any rights or property similar to the foregoing in any part of the world whether registered or unregistered together with the right to apply for the registration of such rights in any part of the world and the rights to current applications for registration of any such intellectual property referred to above. |
| Liability Period | the period from the date of the Sub-Contract until the date 12 years after the date of practical completion of the Sub-Contract Works. |
| Main Contract | the contract dated [DATE] made between the Contractor and the Employer. |
| Main Works | the [design and] construction of the works defined in the Main Contract as the “Works”. |
| [Notice Period | [28] days]. [Delete if clause 14 (Step-in Rights) does not apply] |
| Prohibited Materials | any materials or substances other than in conformity with: the guidance given in the edition current at the date of specification and/or use of the publication “Good Practice in Selection of Construction Materials 2011” published by the British Council for Offices in March 2011; and relevant British Standards or Codes of Practice. |
| Project | the [DESCRIBE PROJECT] at the Site. |
| Site | [DETAILS]. |
| Sub-Contract | the sub-contract dated [DATE] made between the Contractor and the Sub-Contractor. |
| Sub-Contract Works | the [design and] construction of the sub-contract works to be provided by the Sub-Contractor under the Sub-Contract as detailed in the Sub-Contract. |
| [Termination Right | a right which may be or become available to the Sub-Contractor to terminate or treat as terminated or repudiated the Sub-Contract or its engagement under it or discontinue or suspend the performance of any duties or obligations under the Sub-Contract.] [Delete if clause 14 (Step-in Rights) does not apply] |
| [Third Parties | - a) any company, bank or institution providing finance in connection with or secured (whether by charge, sale and leaseback or otherwise) upon the Project - b) any purchaser of the Project or any part of it or - c) any tenant of the Project or any part of it.] [To be included where the Beneficiary is the Employer and clauses 12.2 to 12.4 apply] |

THIS DEED is made on the date set out in the Particulars

- BETWEEN:

- the Sub-Contractor;[and]

- the Beneficiary[; and

- the Contractor]. [To be included where clause 14 (Step-in Rights) applies]

- BACKGROUND:

- The [Beneficiary][Employer] has appointed the Contractor under the Main Contract to provide the Main Works in relation to the Project.

- The Beneficiary’s Interest in the Project is set out in the Particulars.

- The Contractor has appointed the Sub-Contractor under the Sub-Contract to provide the Sub-Contract Works.

- The Sub-Contractor is obliged under the Sub-Contract to give a warranty in this form in favour of the Beneficiary.

- OPERATIVE PROVISIONS

- DEFINITIONS

- Subject to the words defined in the Particulars (which will have that meaning throughout this Deed), the words defined in the Sub-Contract will have the same meaning in this Deed.

- CONSIDERATION

- This Deed is made in consideration of the payment of one pound (£1.00) by the Beneficiary to the Sub-Contractor receipt of which the Sub-Contractor acknowledges.

- SUB-CONTRACTOR’S WARRANTIES

The Sub-Contractor warrants to the Beneficiary that it has performed and will continue to perform its duties under the Sub-Contract in accordance with the Sub-Contract.

The Sub-Contractor further warrants that it has exercised and will continue to exercise reasonable skill and care (or such higher duty as the Sub-Contract imposes) in relation to the following (so far as it is responsible for them):

the design of the Sub-Contract Works;

the selection of goods, materials, equipment or plant for the Sub-Contract Works; and

the satisfaction of any performance requirement or specification of or for the Sub-Contract Works.

INTELLECTUAL PROPERTY RIGHTS

Subject to the following provisions of this Deed, all Intellectual Property in the Documents will remain vested in the Sub-Contractor.

The Sub-Contractor grants (or, if such a grant cannot legally take place until a later date, agrees to grant) to the Beneficiary, with effect from the date of this Deed or in the case of any Intellectual Property not yet in existence with effect from its creation, an irrevocable, royalty-free, non-exclusive licence.

Such licence will:

remain in full force and effect notwithstanding the completion of the Sub-Contractor’s obligations or the termination of the Sub-Contract or this Deed or the determination of the Sub-Contractor’s engagement under the Sub-Contract or any dispute under the Sub-Contract or this Deed;

allow the Beneficiary to use the Intellectual Property and to reproduce all Documents for any purpose whatsoever connected with the Sub-Contract Works including, but without limitation, the execution, completion, maintenance, letting, advertisement, modification, reinstatement and repair of the Sub-Contract Works;

carry the right to grant sub-licences and will be transferable to third parties; and

enable the Beneficiary to use and reproduce the Documents for any extension of the Project, but not include a licence to reproduce the Intellectual Property in the Documents for any extension of the Project.

The Sub-Contractor will not grant to any third party the right to use any of the Documents except under any warranty or third party rights it is obliged to give under the Sub-Contract or under this Deed or as otherwise required to enable it to fulfil its obligations under the Sub-Contract.

The Sub-Contractor will not be liable for any use the Beneficiary may make of the Documents for any purpose other than that for which they were prepared.

The Sub-Contractor warrants that the Documents (except to the extent that duly authorised sub-contractors have been used to prepare the same) are the Sub-Contractor’s own original work and that in any event their use in connection with the Project will not infringe the rights of any third party. The Sub-Contractor further warrants that where duly authorised sub-contractors are used their work will be original and that their work will be covered by the licence granted to the Beneficiary under clause 4.2.

The Sub-Contractor will:

keep electronic copies of the Documents in a readable form for a period of 15 years from practical completion of the Works; and

on reasonable request at any time and following reasonable prior notice to give to the Beneficiary, or those authorised by the Beneficiary, access to the Documents and to provide copies (including electronic copies in a readable form) of the Documents at the Beneficiary’s expense.

The Sub-Contractor waives any moral rights in the Documents or in relation to the Sub-Contract Works that it may have under Part 1 Chapter IV of the Copyright, Designs and Patents Act 1988 or any re-enactment or modification of it and will procure a written waiver in equivalent terms from its employees, its sub-contractors and its sub-contractors’ employees.

- PROHIBITED MATERIALS

The Sub-Contractor warrants to the Beneficiary, [subject to clause 3.2] that, in or in connection with the Sub-Contract Works:

it has not used or permitted to be used or specified, and will not use or specify for use or permit to be used any Prohibited Materials;

it is not aware and has no reason to suspect or believe that Prohibited Materials have been or will be used.

Clause 5 does not create any additional duty for the Sub-Contractor to inspect or check the work of others which is not required by the Sub-Contract.

- INSURANCE

The Sub-Contractor confirms that it has taken out and will maintain the Insurance for the duration of the Liability Period with reputable insurers authorised to carry on business in the United Kingdom.

If such insurance is not available to the Sub-Contractor at commercially reasonable rates and terms (excluding any increase in premiums attributable to the actions, omissions, errors or defaults of the Sub-Contractor), the parties will meet, the Sub-Contractor will outline the steps it intends to take to manage such risks, and the parties will use reasonable endeavours to agree a method of managing such risks.

The Sub-Contractor will provide the Beneficiary with a current broker’s letter confirming that the policies referred to in clause 6 are in full force and effect.

- NO APPROVAL

- The Sub-Contractor’s liabilities under this Deed will not be in any way reduced or extinguished by reason of any inspection or approval of the Documents or attendance at site meetings or other enquiry or inspection which the Beneficiary may make or procure to be made for the Beneficiary’s benefit or on its behalf.

- ASSIGNMENT

- The Beneficiary may, without the consent of the Sub-Contractor [and without prejudice to the provisions of clause 14][Delete if clause 14 (Step In Rights) does not apply], assign any of its rights under this Deed to any person by way of absolute legal assignment, on not more than two occasions only. Any assignment (whether by legal assignment, equitable assignment, charge or otherwise and including re-assignments) to and from any Associate of the Beneficiary or any party providing finance to the Beneficiary (or any Associate of the Beneficiary) will not count towards the number of assignments permitted without consent under clause 8. The Beneficiary will notify the Sub-Contractor of any assignment specifying the name and address of the assignee and the date of the assignment. The Sub-Contractor will not contend that any such assignee is precluded from recovering any loss resulting from any breach of this Deed (whatever the date of such breach) by reason only that that person is an assignee and not the original beneficiary under this Deed or by reason that the original beneficiary or any intermediate beneficiary escaped any loss resulting from such breach by reason of the disposal of any interest in the Site or that the original beneficiary or any intermediate beneficiary has not suffered any or as much loss.

- NOTICES

Any notice or other communication given under or in connection with this Deed must be in writing and sent by first class post, delivered to or left at the recipient’s registered office or, if there is none, its last known address.

Any notice given complying with clause 9.1 will be deemed to be served if given by first class post at 9.00am on the next working day after the date of posting, or if delivered or left at the correct address, on the date of delivery.

- OTHER RIGHTS AND REMEDIES

- The rights and benefits conferred upon the Beneficiary by this Deed are in addition to any other rights and remedies it may have against the Sub-Contractor including, without limitation, any remedies in negligence.

- LIMITATION

The Sub-Contractor has no liability under this Deed which is greater or of longer duration than it would have had if, instead of this Deed, the Beneficiary had been a party to the Sub-Contract as joint employer, provided that the Sub-Contractor will not be entitled to set-off or deduct from any sums payable to the Beneficiary under this Deed any sums due or claimed as due by the Sub-Contractor from the Contractor.

The Sub-Contractor will be entitled in any action or proceedings brought by the Beneficiary under this Deed to rely on any limitation in the Sub-Contract and to raise equivalent rights in defence of liability (but excluding set-offs and counterclaims) as it would have against the Beneficiary if, instead of this Deed, the Beneficiary had been a party to the Sub-Contract as joint employer.

No action or proceedings may be brought or commenced under this Deed at any time after the Liability Period provided that:

any action under statute may be brought or commenced within any longer prescribed statutory limitation period;

any such action or proceedings for breach of this Deed which relate to a Building Safety Liability may be brought or commenced before the expiry of the limitation period which applies to the Building Safety Liability or the Civil Liability (Contribution) Act 1978; and

the parties shall not plead in defence of any action or proceedings referred to in clauses 11.3.1 and 11.3.2 any shorter limitation period whether under the Limitation Act 1980 or otherwise.

- THIRD PARTY RIGHTS

[Subject to clause 12.2, the] [This wording, and clauses 12.2 to 12.4 only to be included in warranty in favour of the Employer] [The] parties do not intend that any term of this Deed will be enforceable by any person under the Contracts (Rights of Third Parties) Act 1999, except that any Associate of the Beneficiary may in its own right enforce a term of this Deed.

[The Beneficiary and the Sub-Contractor agree that, notwithstanding any other provision of this Deed, unless the Sub-Contractor has already provided a collateral warranty to the relevant Third Party in accordance with the terms of the Main Contract, the rights set out in this Deed will vest in the Third Parties on the date on which the Beneficiary issues a notice to that effect to the Sub-Contractor, stating the name of the relevant Third Party, the nature of its interest in the Main Works and the relevant clauses of this Deed that will apply.

Subject to clause 12.4, the Beneficiary and the Sub-Contractor will be entitled to:

agree any waiver or release under or arising from or in respect of this Deed; and

agree to settle any dispute or other matter arising out of or in connection with this Deed,

in each case in or on such terms as they, in their absolute discretion, think fit, without the consent of any of the Third Parties.

After the rights have vested in a Third Party in accordance with clause 12.2 the Beneficiary and the Sub-Contractor will not be entitled to amend or vary the express provisions of this Deed without the consent of the relevant Third Party.]

- GOVERNING LAW AND JURISDICTION

This Deed and any non-contractual obligations arising out of or in connection with it will be governed by English law.

The courts of England and Wales have exclusive jurisdiction to determine any dispute arising out of or in connection with this Deed (including, without limitation, in relation to any non-contractual obligations). The parties irrevocably submit to the jurisdiction of those courts.

- [STEP-IN RIGHTS [Delete if Step-In Rights are not to apply]

Subject to clause 14.8, the Sub-Contractor will not exercise or seek to exercise any Termination Right without first giving to the Beneficiary a notice which:

is served not less than the Notice Period before the exercise of the Termination Right;

states the Sub-Contractor’s intention to exercise the Termination Right; and

specifies the Sub-Contractor’s grounds for exercising the Termination Right and states the amount (if any) of monies outstanding under the Sub-Contract.

Within the Notice Period the Beneficiary may give notice to the Sub-Contractor expressly confirming its intention to comply with clause 14.3.2 and that the Beneficiary will become the employer under the Sub-Contract to the exclusion of the Contractor and, upon giving such notice, that will be the case and the Sub-Contract will be and remain in full force and effect notwithstanding any of the grounds in the Sub-Contractor’s notice under clause 14.1.

If the Beneficiary has given notice under clause 14.2 or under clause 14.5, the Beneficiary will:

as soon as practicable remedy any outstanding breach by the Contractor; and

from the date of the Sub-Contractor’s notice (if the Beneficiary has given notice under clause 14.2) or the date of the Beneficiary’s notice (if the Beneficiary has given notice under clause 14.5), become responsible for all sums properly payable to the Sub-Contractor under the Sub-Contract and for the observance and performance of all of the other duties and obligations on the part of the contractor to be observed and performed under the Sub-Contract accruing due after the service of such Sub-Contractor’s notice or Beneficiary’s notice (as applicable) but the Beneficiary will in paying such sums be entitled to the same rights of set-off and deduction as would have applied to the Contractor under the Sub-Contract.

Notwithstanding anything contained in this Deed and notwithstanding any payments which may be made by the Beneficiary to the Sub-Contractor the Beneficiary will not be under any obligation to the Sub-Contractor nor will the Sub-Contractor have any claim or cause of action against the Beneficiary unless and until the Beneficiary has given notice to the Sub-Contractor under either clause 14.2 or clause 14.5.

If requested by the Beneficiary by notice expressly confirming the Beneficiary’s intention to comply with clause 14.3.2 and subject to clause 14.3.1 and clause 14.3.2, the Sub-Contractor agrees to accept the instructions of the Beneficiary to the exclusion of the Contractor in respect of the Sub-Contract Works upon the terms and conditions of the Sub-Contract. The Beneficiary will then become the employer under the Sub-Contract to the exclusion of the Contractor and the Sub-Contractor will, if so requested, enter into a novation agreement to confirm the substitution of the Beneficiary for the Contractor under the Sub-Contract.

The Contractor acknowledges that the Sub-Contractor will be entitled to rely on a notice given to the Sub-Contractor by the Beneficiary under clause 14.5 as conclusive evidence that the Beneficiary is entitled to serve such notice.

The Beneficiary may by notice to the Sub-Contractor appoint another person to exercise its rights under clause 14 subject to the Beneficiary remaining liable to the Sub-Contractor as guarantor for its appointee in respect of its obligations under this Deed.

Where the Sub-Contractor is seeking to exercise a right to suspend the performance of any duties or obligations under the Sub-Contract as a result of non-payment or in accordance with s112 of the Housing Grants, Construction and Regeneration Act 1996, the Sub-Contractor will give to the Beneficiary notice of its intention so to do at the same time as it serves notice on the Contractor.

Notwithstanding the other provisions of clause 14, if the Sub-Contract has for any reason been terminated prior to receipt by the Sub-Contractor of the Beneficiary’s notice under clause 14.2 or clause 14.5, the Sub-Contractor will on receipt of the Beneficiary’s notice enter into a new sub-contract with the Beneficiary on the same terms as the Sub-Contract to continue the Sub-Contract Works in all respects as if the Sub-Contract had been transferred to the Beneficiary in accordance with the provisions of clause 14.

[Where the Sub-Contractor has given rights in relation to the Sub-Contract similar to those contained in clause 14 to any other person then if both the Beneficiary and any such other person serve notice under clause 14.2 or clause 14.5 or its equivalent the notice served by the Beneficiary will [prevail][not prevail] [not prevail over any notice served by [NAME] but prevail over any notice served by any other person]].]

- COUNTERPARTS

This Deed may be executed in any number of counterparts, each of which will constitute an original, but which will together constitute one agreement.

- THIS DOCUMENT is executed as a deed and delivered on the date stated in the Particulars.

- [ALL PARTIES TO EXECUTE]

SCHEDULE 8

CONTRACT DOCUMENTS LIST

- The Contract Documents comprise the following documents numbered/listed:

- Insert here the list acquired from the Employer or the Employer’s Agent, which sets out the technical contract documents that are incorporated via email or file transfer. This list should include identifiable references, such as the document name, date and version number.